## Onboarding Milestones
Welcome to Arbor
Over the next 8 weeks, you will use this workbook to help you set up your new Arbor MIS! Each page is designed to help you keep track of the onboarding project and guide you through what to do at each week, in additon to the training that is available via the Arbor Training Hub. As well as this workbook, we also have lots of information on our helpcentre here.
Key Onboarding Milestones
This tab contains an overview of the tasks you will complete during your 8 week onboarding journey and when you should do them. You should update this regularly to help you keep track of your progress. | ✔ | = Complete
| ✖ | = Delayed
| ▲ | = In Progress
Milestone | Status | Due | Owner
Log into Arbor Training Hub |  | Week 1 | School Project Lead
Complete Manual Migration Training Module: Onboarding |  | Week 1 | School Project Lead
Blank Arbor site released |  | Week 1 | Arbor Onboarding Team
Log into blank Arbor site |  | Week 1 | School Project Lead
Complete Manual Migration Training Module: Week 1 |  | Week 1 | School Project Lead
Add School Details and Pastoral Structure to Arbor site |  | Week 1 | School Project Lead
Create staff profiles for any additional staff who will be helping with site setup |  | Week 1 | School Project Lead
Complete Manual Migration Training Module: Week 2 |  | Week 2 | School Project Lead
Start to book onboarding training via the Arbor Training Hub |  | Week 2 | School Project Lead
Download all Entity Importer spreadsheets |  | Week 2 | School Project Lead
Test importing the 'Staff Template' with 2 staff members into your Arbor site so you feel comfortable with the process |  | Week 2 | School Project Lead
Continue to enter data to entity importer spreadsheets, utilise your 'Data Entry Checklist' to track your progress |  | Week 2 | School Project Lead
Appoint a change controller to document any changes made in your current MIS as these will need to be reflected in your templates |  | Week 2 | School Project Lead
Contact any 3rd party apps and information them of your move to Arbor |  | Week 2 | School Project Lead
Complete Manual Migration Training Module: Week 3 |  | Week 3 | School Project Lead
Continue to book/attend onboarding training |  | Week 3 | School Project Lead
Continue entering your data into your Entity Importer Spreadsheets |  | Week 3 | School Project Lead
Ensure your change controller documents any changes made in your current MIS as these will need to be reflected in your entity importer spreadsheets |  | Week 3 | School Project Lead
Complete Manual Migration Training Module: Week 4 |  | Week 4 | School Project Lead
Test Importing 2 Student CTF's |  | Week 4 | School Project Lead
Once happy with process, import all CTFs |  | Week 4 | School Project Lead
Once you've imported student CTFs - let Arbor know, we will run a script to amend their enrolment dates |  | Week 4 | School Project Lead
Update enrolment dates |  | Week 4 | Arbor
Continue populating your Entity Importer spreadsheets |  | Week 4 | School Project Lead
Complete Manual Migration Training Module: Week 5 |  | Week 5 | School Project Lead
Start importing your populated Entity Importer spreadsheets |  | Week 5 | School Project Lead
Start setting up your Day 1 Modules (modules that you need from Go-Live, e.g. Meals & Payments) |  | Week 5 | School Project Lead
Request attendance data from your current MIS, to upload into Arbor using the Attendance Entity Importer |  | Week 5 | School Project Lead
Complete Manual Migration Training Module: Week 6 |  | Week 6 | School Project Lead
Import any remaining Entity Importers/add any outstanding data |  | Week 6 | School Project Lead
Confirm that your Registers are available for Day 1 |  | Week 6 | School Project Lead
Share URL with wider team and advise how to log in |  | Week 6 | School Project Lead
Go Live - start using Arbor to take daily registers |  | Week 7 | School Project Lead
Complete Manual Migration Training Module: Week 7 |  | Week 7 | School Project Lead
Start Post Launch Onboarding Training |  | Week 7 | School Project Lead
Check in with staff, ensure all are aware of support options etc |  | Week 7 | School Project Lead
Connect 3rd party applications |  | Week 7 | School Project Lead
Complete Manual Migration Training Module: Week 8 |  | Week 8 | School Project Lead
Complete any outstanding training |  | Week 8 | School Project Lead
Ensure you have attendance data from previous MIS to import before next census |  | Week 8 | School Project Lead
Introduction from Account Management Team |  | Week 8 | Arbor Account Management
Onboarding complete |  | Week 8 | School Project Lead

## Data Entry Checklist
Site Setup & Data Entry Checklist
Use this tab to keep track of your progress when entering data into your blank Arbor MIS - all data listed below will need to be added into your Arbor site by the school Project Lead and you can access the relevant training videos via the Manual Migration course in the Arbor Training Hub. |  |  | ✔ | = Complete
|  |  | ✖ | = Delayed
|  |  | ▲ | = In Progress
School Details and Pastoral Structure | Additional Info | When to add | How to add | Training | Progress
School Details |  | Week 1 | Manually |  | Complete
Academic Years |  | Week 1 | Manually |  | Delayed
Term Dates |  | Week 1 | Manually |  | In Progress
Holidays |  | Week 1 | Manually
Year Groups |  | Week 1 | Manually
Registration Forms |  | Week 1 | Manually
Houses |  | Week 1 | Manually
Staff Information | Additional Info | When to add | How to add | Training | Progress
Staff Information | Ensure email addresses are added | Start week 2, complete by week 6 | In bulk via Entity Importer
Pay Scale | If this data is currently stored outside of your MIS this might not be applicable to your school to upload into Arbor | Start week 2, complete by week 6 | In bulk via Entity Importer
Pay Scale Spinal Point | If this data is currently stored outside of your MIS this might not be applicable to your school to upload into Arbor | Start week 2, complete by week 6 | In bulk via Entity Importer
Staff Contract | If this data is currently stored outside of your MIS this might not be applicable to your school to upload into Arbor | Start week 2, complete by week 6 | In bulk via Entity Importer
Staff Absence |  | Start week 2, complete by week 6 | In bulk via Entity Importer
Staff Check |  | Start week 2, complete by week 6 | In bulk via Entity Importer
Staff Qualification |  | Start week 2, complete by week 6 | In bulk via Entity Importer
Teacher Status | See here how to add this in bulk | Start week 2, complete by week 6 | Manually
Staff Next of Kin | Not required for Census
Staff Vehicle | Not required for Census
Student Data | Additional Info | When to add | How to add | Training | Progress
Add an Intake Season |  | Complete by week 6 | Manually
Import all Student CTF's (previous & current academic year) | - Include those that left mid-year - If you add your CTFs twice this will cause duplication issues | Complete by week 6 | Manually
Enrol students from this Current Academic Year onto your Arbor Site |  | Complete by week 6 | Manually
Off-role students that have left mid-year |  | Complete by week 6 | Manually
Correct start dates for those that started mid-year |  | Complete by week 6 | Manually
Dietary Requirements |  | Complete by week 6 | In bulk via Entity Importer
Disability Access Funding |  | Complete by week 6 | In bulk via Entity Importer
Early Years Pupil Premium Recipient |  | Complete by week 6 | In bulk via Entity Importer
Fixed Period Exclusions |  | Complete by week 6 | In bulk via Entity Importer
Hours At Setting |  | Complete by week 6 | In bulk via Entity Importer
Medical Conditions |  | Complete by week 6 | In bulk via Entity Importer
Permanent Exclusion |  | Complete by week 6 | In bulk via Entity Importer
Top Up Funding |  | Complete by week 6 | In bulk via Entity Importer
Post Looked After Arrangements |  | Complete by week 6 | Manually
Young Carer |  | Complete by week 6 | In bulk via Entity Importer
Guardian Relationship Template | Not applicable if importing students via CTF | Complete by week 6 | In bulk via Entity Importer
Student Consents | Not required for Census | Complete by week 6 | Manually
Student Linked documents | Not required for Census | Complete by week 6 | Manually
Student Pastoral Note Template | Not required for Census | Complete by week 6 | In bulk via Entity Importer
Attendance Data |  | By next census | In bulk via Entity Importer

## Training Information
Arbor Training Hub
Over the next 8 weeks, you'll complete all of your training via the Arbor Training Hub. The Project Lead at your school already has an account on the Hub, and can log in using the details below: Training Hub Link: https://arbor-education.learnupon.com Username: Your work email address Temporary password: Traininghub1 You have also been sent these details via email, and can share the details in that email with your wider team so they can create accounts on the Hub Top Tip: Bookmark the link for the Arbor Training Hub, as you'll be using the Training Hub a lot over the next few weeks as you watch videos and attend training to help you get up and running with Arbor!
Manual Migration Site Setup Training
In the Arbor Training Hub, head to the course Manual Migrations Site Setup Training, and complete the following training modules:
Module
Week 1 - Setting up school details and adding pastoral structure | Week 5 - The Attendance Data Template
Week 2 - Entity Importers | Week 6 - Final steps before Go-Live
Week 3 - The Staff Profile | Week 7 - Go-Live!
Week 4 - The Student Profile and CTF's | Week 8 - Onboarding complete
Following on from each session, you should feel comfortable adding the relevant data into your blank Arbor MIS
Onboarding Training
The onboarding training is all available to complete in the Arbor Training Hub and broken down in to the separate courses below:
Complete Before Go Live | Post Go Live
001: Getting Started | 007: Adding further information on Student Profiles (SEN needs)
002: Teacher Essentials | 010: Single Central Record
003: Managing Student & Enrolment | 011: Staff Contracts and Pay Scales
004: Guardian Profiles | 012: Custom Groups
005: Managing Staff Profiles | 012: User Defined Fields
006: Staff Business Roles and Permissions | 013: School Reporting on Arbor
007: Staff Absence and Cover | 014: Introduction to Custom Report Writer
008: Primary Attendance
008: Attendance Reporting
009: Arbor MIS Management
011: Communications
Additional Training
You may have also purchased additional training, to help you roll out modules such as meals, payments, assessments or behaviour. If you have purchased these, you will be able to book these courses in the Arbor Training Hub whenever you’re ready to setup these areas of Arbor! If you have any questions about the training you've purchased, please contact myonboarding@arbor-education.com