## 1. Onboarding Checklist
Weekly Onboarding Checklist
Week 1 | Status
Join a Kick-Off Webinar - you can find the booking links in your Week 1 email
Complete the Survey in your Training Email to register additional users for the Training Hub - Click Here for more info
Log in to the Arbor Training Hub and start booking some live sessions. Use tab 4. Training in this workbook to track your progress
Make a plan for your Migration Day! - Migration Day Guide
Week 2 | Status
Begin your Pre-migration Data Cleansing and Counts using tab 2 and 3 of this workbook
Contact your 3rd parties and let them know you're moving to Arbor - More info on 3rd parties can be found here
Sign up to Arbor HQ!
Week 3 | Status
Continue your Pre-migration Data Cleansing and Counts using tab 2 and 3
Look out for your Secure Upload Portal - let us know if you don't receive this by emailing myonboarding@arbor-education.com
Continue to complete your Arbor Foundation training
Week 4 - Migration Week! | Status
Continue to complete your Arbor Foundation Training
Ensure your data cleanses and counts have been completed before migration day - use tab 2 and 3 of this workbook
Migration Day - log in to your Secure Upload Portal to start your migration. Full instructions here.
Week 5 - Go Live Week! | Status
Log in to your new Arbor site and read our Getting Started guide to help you get going!
Share your Arbor URL with the rest of your team so they can log in - click here for our login issues troubleshooting guide
Approve any 3rd party connections in Arbor
Start taking attendance in Arbor!
Week 6 & 7 | Status
Download and review your Data Migration Report - sign this off when you're happy with the data on Arbor following migration
Raise any data migration issues with Support *please note - if you are a partner supported school, you will need to raise migration issues with your Support Partner
Week 8 | Status
Complete any outstanding Arbor Foundations Training
Make sure you've signed up to Arbor HQ!
You'll complete onboarding at the end of this week. Our team of Customer Success Managers will work with you from this point onwards to ensure long term success on Arbor - they'll reach out to you after Week 8 to introduce themselves. This team can be reached at mysuccess@arbor-education.com

## 2. Pre-migration data cleansing
Pre Migration Data Checks & Cleansing
We've prepared these data checks and cleansing tasks for you to complete in your current MIS. This will help to make sure that the data we import to your new Arbor system is as accurate as is possible. You must confirm that you have completed these data checks on your Secure Upload Portal before sending us your data. If you don't, we won't be able to migrate your data.
Ref | Field | What should I check? | Why do I need to check this? | How do I clean it up? | Status
Staff Data
1.1 | Staff Email | Check that staff have a work email address on their staff profile. | This will become their Arbor username. Staff will not be able to log in to Arbor without an email address. | Add a work email address to their profile. For SIMS users, this will need to be set as main and primary.
1.2 |  | Check that all staff emails are accurate and do not have any typos or errors | This will become their Arbor username. Staff will not be able to log in to Arbor without an email address. | Amend any errors
1.3 |  | Check that staff work email address are only used once in your current MIS. i.e. Any staff members who have guardian profiles at the school must have a personal email only on their guardian profile. | If staff email appears on a guardian profile following migration, that staff member will not be able to log in to Arbor until it is removed. | Make sure that all information is in the right place (e.g. no street names in the Post Code field), and that addresses are correct. Make sure historic addresses have an end date
1.4 | Staff Contracts | Check that any old staff contracts and roles have an end date. | If historic staff do not have an end date on their contract and role, they will migrate as active staff members, and you'll need to delete them from Arbor. | Add end dates to all contracts and roles
1.5 | Duplicate Staff | Run a report on staff to identify duplicates | Duplicate staff records will prevent staff from logging into Arbor. | Resolve any duplicates. If you can't do this in your current MIS, make a plan to do it in Arbor after Go Live.
1.6 | Phone Numbers | Run a report on staff contact numbers and check that none have non-number characters (International dialling codes and spaces are accepted). | Phone numbers that include a special character (e.g. *) will not be imported. | Remove special characters. If there is more than one phone number in a single field, split them into one field per phone number.
Student Data
2.1 | Demographics (Pupil Premium Eligibility) | Check that FSM eligibility is set correctly, with a start and end date (if applicable) | Arbor derives PP eligibility based on the eligibilty criteria. We do not have a PP tick box like some MIS. If there is no underlying eligibility criteria, students will not show as PP eligible. If no end date is recorded for these criteria, they will show as Ongoing | Make sure that any relevant demographic criteria has a start and an end date
2.2 |  | Check that Ever6FSM eligibility is set correctly, with a start and end date (if applicable)
2.3 |  | Check that In Care / Care Leaver status is set correctly, with a start and end date (if applicable)
2.4 |  | Check that Service Child status is set correctly, with a start and end date (if applicable)
2.5 | SEN Students | Check that SEN status is set correctly, with a start and end date (if applicable) | If a SEN Status has an end date, the student will not appear as SEN in Arbor. In SIMS, this will appear in the Status History. | Make sure that all SEN students have correct start and end dates on their SEN Status, Categories and Needs
2.6 |  | Check that SEN Categories and Needs are set correctly, with a start and end date (if applicable)
2.7 | Duplicate Students | Run a report on enrolled students and applicants to identify duplicates. | Duplicate students will impact your number on roll, statutory returns and could present a safeguarding risk | Resolve any duplicates. If you can't do this in your current MIS, make a plan to do it in Arbor after Go Live.
2.8 | Addresses | Run a report on student addresses and check that they look correct, with the right information in the right field (e.g. Post Codes only in the Post Code field) | Accurate address information will be needed to effectively use Arbor's communication functionality. | Make sure that all information is in the right place (e.g. no street names in the Post Code field), and that addresses are correct. Make sure historic addresses have an end date
2.9 | Historic Records | Check your school's policy for data retention and delete records that are beyond the retention period | Holding data beyond the retention period is a breach of GDPR. | Delete the unwanted records. If you can't do this in your current MIS, it's easy to do in Arbor
Guardian Data
3.1 | Guardian Records | Check that each guardian has their own record (e.g. Mr & Mrs Smith should be 2 separate records) | Needed for accurate guardian contact information to migrate to Arbor | Split any merged records so that each guardian has their own
3.2 | Duplicate Guardians | Run a report on guardians to identify duplicates. | Duplicate guardian records will impact the use of communications, and in some cases could present a safeguarding risk | Resolve any duplicates. If you can't do this in your current MIS, make a plan to do it in Arbor after Go Live.
3.3 | Addresses | Run a report on guardian addresses and check that they look correct, with the right information in the right field (e.g. Post Codes only in the Post Code field) | Accurate address information will be needed to effectively use Arbor's communication functionality. | Make sure that all information is in the right place (e.g. no street names in the Post Code field), and that addresses are correct. Make sure historic addresses have an end date
3.4 | Phone Numbers | Run a report on guardian contact numbers and check that none have non-number characters (International dialling codes and spaces are accepted). | Phone numbers that include a special character (e.g. *) will not be imported. | Remove special characters. If there is more than one phone number in a single field, split them into one field per phone number.
3.5 | Guardian Contact Details | Check that all guardian contact details are stored in the guardian section of the profile, and not as student contact details. | Guardian contact details that are stored as Student contact details will migrate to the Student profile, not the guardian profile. | Move guardian details to the correct place on the profile. For example, SIMS users should ensure guardian contact details are stored in section 5 "Family and Home"
3.6 | Parental Responsibility status | Check that each student has a primary guardian with parental responsibility set correctly. | Guardians with Parental Responsibility will be set as 'Primary Guardians' in Arbor, and will receive communications for that child. If this is inaccurate, there may be a safeguarding risk. | Add or remove parental responsibility as required. (e.g. a grandparent may be authorised to collect, but this doesn't mean they have parental responsibility).
3.7 | Guardians without Linked Students | Run a report on guardians, and check that there are no guardians without a linked student | Guardians with no linked students will need to be deleted, as it's unlikely you have a basis for holding the data. | Link guardians to a student, or delete the records. If you're not able to do this in your current MIS, you can do it in Arbor after go live.

## 3.Data Counts
Data Counts
Field | What should I count? | Number in Bromcom | Number in Arbor | Checked By | Status
Enrolment | Count of whole school enrolment | e.g 307 | e.g 307 | e.g Joe Bloggs
Count of enrolment by Year Group
Count of enrolment by Registration Form
Demographic | Count of students with FSM status
Count of students with Ever6FSM status
Count of students with Service Child status
Count of students with Pupil Premium eligibility
Count of students with EYPP eligibility
Count of students with Service Child status
SEN | Count of students with SEN Status
Count of Students by SEN Need To check this in Arbor navigate to Students > Educational Needs > Students with SEN > SEN Needs
Staff | Count of staff this academic year To check this in Arbor navigate to School > All Staff > Single Central Record
Attendance | Percentage Present for Academic YTD To check this in Arbor navigate to Students > Attendance > Statistics > Use filter to change date and type
Percentage Absent for Academic YTD To check this in Arbor navigate to Students > Attendance > Statistics > Use filter to change date and type
Percentage Authorised Absent for Academic YTD To check this in Arbor navigate to Students > Attendance > Statistics > Use filter to change date and type
Percentage Unauthorised Absent for Academic YTD To check this in Arbor navigate to Students > Attendance > Statistics > Use filter to change date and type

## 4. Training
Training
The Arbor Training Hub - Click Here
Your Project Lead will automatically be enrolled into the Arbor Training Hub, and have access to the 'Primary Deep Dive' Learning Path, which includes all Arbor Foundation courses. Your Project Lead will also be assigned any additional bespoke training the school has purchased. To nominate additional users for the Training Hub, please complete the nomination survey sent in your Training Email (week 1) When new users login, they will be asked to choose a learning path. Click here to see which courses are included in each Learning Path.
Teacher Training
Teachers don't normally need access to the Arbor Training Hub - You can share this Getting Started and Teacher Essentials course with them instead.
Arbor Foundations Training
Recommended to complete before Go-Live
| Available as: | Duration: | Status:
Arbor Foundations: Getting Started | Video Content | 13 mins
Arbor Foundations: Student Profiles & Enrolment | Instructor-led training | 90 mins
Arbor Foundations: Guardian Profiles | Video Content | 45 mins
Arbor Foundations: Managing Staff Profiles | Instructor-led training | 45 mins
Arbor Foundations: Staff Business Roles and Permissions | Instructor-led training | 90 mins
Arbor Foundations: Primary Attendance | Instructor-led training | 90 mins
Arbor Foundations: Communications | Instructor-led training | 90 mins
Arbor Foundations: Arbor MIS Management | Video Content | 12 mins
Arbor Foundations: Attendance Reporting | Instructor-led training | 60 mins
Arbor Foundations: Staff Absence and Cover | Instructor-led training | 45 mins
Recommended to complete after Go-Live
Arbor Foundations: Adding Further Information on Student Profiles | Instructor-led training | 75 mins
Arbor Foundations: Single Central Record | Video Content | 15 mins
Arbor Foundations: Staff Contracts and Payscales | Instructor-led training | 45 mins
Arbor Foundations: Custom Groups | Video Content | 23 mins
Arbor Foundations: User Defined Fields | Video Content | 12 mins
Arbor Foundations: School Reporting on Arbor | Video Content | 20 mins
Arbor Foundations: Introduction to Custom Report Writer | Instructor-led training | 75 mins
Arbor Foundations: Interventions | Instructor-led training | 75 mins
Click here to see our Training Schedule
*Please note* all instructor led training is also available as Video Content on the Training Hub
Additional Training
You may have purchased some additional training to help get you up and running with bespoke modules. Any additional training will automatically be added to the Project Lead's Training Hub account. If you would like to discuss purchasing any of the additional training listed below, please contact customersales@arbor-education.com
| Available as: |  | Status:
Arbor Foundations: Meals Setup and Management | Video Content
Arbor Foundations: Parental Engagement | Video Content
Arbor Foundations: Payments Setup and Management | Video Content
Arbor Foundations: Payments Plus | Video Content
Behaviour Consultation and Reporting | Bespoke 1-1
Assessment Consultation | Bespoke 1-1
Operational Reporting | Bespoke 1-1
How to book 1-1 sessions

## 5. Key Documents
Key Documents
Help Centre Articles:
Roles and Responsibilties
Pre-migration Data Cleansing
Migration Guide
Common Migration FAQ's
Getting Started with your Arbor MIS
Signing off your migration report
Training Test Site:
URL: https://primary-training1.uk.arbor.sc/ Login details will be available in the Training email and the Primary Onboarding Workbooks attached to the week 1 email.
Admin Login: | Teacher Login: | Headteacher Login:
Username: ***** | Username: ***** | Username: *****
Password: ******* | Password: ******* | Password: *******