## 1. Onboarding Checklist
Weekly Onboarding Checklist
Welcome to Arbor, we're excited to have you onboard! Use this workbook to keep track of the key tasks you need to complete over the next 8 weeks as you transition to Arbor. Please review each tab of the workbook carefully as this has everything you'll need to action for a successful move.
Week 1 Checklist
1. Join a Kick Off Webinar or watch a recording of the session - Click here for more information and to book | FALSE
2. Complete the form in your Training Email to register additional staff members for the Training Hub - Click Here for more info | FALSE
3. Log in to the Arbor Training Hub and start booking some live sessions. Use tab 4. Training Checklist in this workbook to track your progress | FALSE
4. Read this guide to ensure you understand how the migration from Bromcom to Arbor works and that you have a plan for your migration day | FALSE
Week 2 Checklist
1. Begin your Pre-migration Data Cleansing and Counts using tab 2. Pre-Migration Data Cleansing and 3. Data Counts of this workbook | FALSE
2. Contact your 3rd parties and let them know you're moving to Arbor - Guide to third party APIs | FALSE
3. Review our help centre guidance here, to see our common migration FAQs and more information on how data migrates to Arbor | FALSE
4. Continue training via the Arbor Training Hub, (you can use Tab 4. Training Checklist in this workbook to track progress) | FALSE
Week 3 Checklist
1. Continue your Pre-migration Data Cleansing (tab 2. Pre-Migration Data Cleansing will help you with this) | FALSE
2. Look out for your Secure Upload Portal - let us know if you don't receive this by emailing myonboarding@arbor-education.com | FALSE
3. Share this Teacher Essentials Training so your teaching staff know how to use Arbor when you Go Live | FALSE
Week 4 Checklist - Migration Week!
1. Continue training via the Arbor Training Hub, (you can use Tab 4. Training Checklist in this workbook to track progress) | FALSE
2. Complete data counts using tab 3. Data Counts in this workbook | FALSE
3. Ensure all previous steps have been completed as this week your migration to Arbor begins! | FALSE
4. Log into the Secure Upload Portal on your migration day and upload your Bromcom backup | FALSE
Week 5 Checklist - Go Live Week!
1. Log in to your new Arbor site and read our Getting Started guide to help you get going! | FALSE
2. Share your Arbor URL with the rest of your team so they can log in - click here for our login issues troubleshooting guide | FALSE
3. Share our "Getting Started with Arbor" help centre guidance with your team | FALSE
4. Start taking attendance in Arbor! | FALSE
5. Download and review your Data Migration Report - use this to help check the data in Arbor and sign this off when you're happy with the data on Arbor following migration | FALSE
Week 6 Checklist
1. Finalise all of your data checks in Arbor and sign off your data migration report | FALSE
2. Raise any data migration issues with Support - Please note if you are a partner supported school, you will need to raise migration issues with your Support Partner | FALSE
3. Approve any 3rd party connections in Arbor | FALSE
4. Familiarise yourself with how to contact support for any 'how to' questions | FALSE
Weeks 7 & 8 Checklist
1. Complete any outstanding Arbor Foundations Training | FALSE
2. Make sure you've signed up to Arbor HQ! This is our community, where you can speak to other Arbor schools to share best practise and top tips! | FALSE
At the end of week 8, your onboarding is complete! If you have Arbor Support, our Customer Success Team will work with you from this point onwards to ensure long term success on Arbor. If you are supported by a Partner, your partner will continue to work with you moving forward.

## 2. Pre-Migration Data Cleansing
Pre Migration Data Checks & Cleansing
We've prepared these data checks and cleansing tasks for you to complete in Bromcom. They will help to make sure that the data we import to your new Arbor system is as accurate, up to date and tidy as is possible. You must complete the data cleansing before your migration to Arbor.
Ref | Field | What should I check? | Why do I need to check this? | How do I clean it up? | Status
Staff Data
1.1 | Staff Email | Check that staff have a work email address on their staff profile in Bromcom | This will become their Arbor username. Staff will not be able to log in to Arbor without an email address. Click here for more information on how we migrate email addresses. | Add a work email address to their profile. Ensure their work email address is set as 'Primary' email.
1.2 |  | Check that all staff emails are accurate, up to date and do not have any typos or errors | Their email address will become their Arbor username. Staff will not be able to log in to Arbor without an email address. | Amend any errors.
1.3 |  | Check that staff work email addresses are only used once in your current MIS - any staff members who are or have been guardians at the school must not have their work email attached to a student or guardian profile | Having the same email in Bromcom multiple times will cause duplicate profiles to be create in Arbor during the migration. These will need to be resolved in Arbor following the migration using this guide. Guardian profiles in Arbor are created using the guardian details from Student Profiles. If staff email appears on a guardian profile following migration, that staff member will not be able to log in to Arbor until it is removed and replaced with a personal email. | Ensure that staff email addresses are only used for staff profiles in Bromcom. If a staff member is also a guardian, their personal email should be used against Student & Guardian information in Bromcom and their work/staff email address only present once in Bromcom
1.4 | Staff Contracts | Check that any old staff contracts and roles have an end date | If historic staff do not have an end date on their contract and role, they will migrate as active staff members, and you'll need to delete them from Arbor | Add end dates to all contracts and roles
1.5 | Duplicate Staff | Check staff to identify duplicates | Duplicate staff records will prevent staff from logging into Arbor | Resolve any duplicate profiles in Bromcom. If you can't do this in your current MIS, make a plan to do it in Arbor after Go Live. Here's a guide on Resolving Staff duplicates in Arbor
1.6 | Staff Phone Numbers | Check staff contact numbers and ensure that none have non-number characters (International dialling codes and spaces are accepted) | Phone numbers that include a special character (e.g. *) will not be imported. Click here fore more information on how we migrate phone numbers | Remove special characters from number, and if there is more than one phone number in a single field, split them into one field per phone number
1.7 | Historic Staff Records | Check your school's policy for data retention and delete records that are beyond the retention period | We will migrate all the historic data into Arbor, and holding data beyond the retention period is a breach of GDPR, so this will need to be amended in Bromcom before the migration or after the migration in Arbor | Delete the records that you no longer need to keep in line with your Data Retention Policy. If you are unable to delete all historic records before migration, it's easy to do in Arbor afterwards. This guide explains how: Managing data retention in Arbor
Student Data
2.1 | Student Demographics (Pupil Premium Eligibility) | Check that FSM eligibility is set correctly, with a start and end date (if applicable) | Arbor derives PP eligibility based on the eligibilty criteria. We do not have a PP tick box like some MIS, so the eligibilty criteria must be listed in Bromcom to migrate over to Arbor. If there is no underlying eligibility criteria (such as FSM, Looked After, Service Child), students will not show as PP eligible in Arbor after the migration. If no end date is recorded for these criteria, they will show as Ongoing in Arbor. Click here for more information on Pupil Premium in Arbor. | Make sure that any relevant demographic criteria has a start and an end date. This criteria can be found under the 'additional' tab of student profiles.
2.2 |  | Check that Ever6FSM eligibility is set correctly, with a start and end date (if applicable)
2.3 |  | Check that In Care / Care Leaver status is set correctly, with a start and end date (if applicable) - Click here to see how we migrate LAC
2.4 |  | Check that Service Child status is set correctly, with a start and end date (if applicable) - Click here to see how we migrate this information
2.5 | SEN Students | Check that SEN status is set correctly, with a start and end date (if applicable) | If a SEN Status has an end date that has passed, the student will not appear as SEN in Arbor, if there is no end date, they will show as Ongoing in Arbor | Make sure that all SEN students have correct start and end dates on their SEN Status, Categories and Needs.
2.6 |  | Check that SEN Categories and Needs are set correctly, with a start and end date (if applicable)
2.7 | Student Medical Information | Confirm students have a relevant Medical Condition added | To ensure students have correct medical condition Click here for more information on how this data migrates | Check/amend/update in Bromcom.
2.8 | Duplicate Students | Check enrolled students and applicants to identify duplicates | Duplicate students will impact your number on roll, statutory returns and could present a safeguarding risk | Resolve any duplicate student profiles in Bromcom. If you can't do this in Bromcom, make a plan to do it in Arbor after Go Live using this guidance - Resolve duplicate students in Arbor
2.9 | Student Addresses | Check that student addresses look correct, with the right information in the right field (e.g. Post Codes only in the Post Code field) | Accurate address information will be needed to effectively use Arbor's communication functionality - click here to see how we migrate this information | Make sure that all information is in the right place (e.g. no street names in the Post Code field), and that addresses are correct and up to date. Make sure historic addresses have an end date.
2.1 | Historic Student Records | Check your school's policy for data retention and delete records that are beyond the retention period | Holding data beyond the retention period is a breach of GDPR, so this will need to be amended in Bromcom before the migration or after the migration in Arbor | Delete the records that you no longer need to keep in line with your Data Retention Policy. If you are unable to delete all historic records before migration, it's easy to do in Arbor afterwards. This guide explains how: Managing data retention in Arbor
Guardian Data
3.1 | Guardian Records | Check that each guardian has their own record (e.g. Mr & Mrs Smith should be 2 separate records) | Needed for accurate guardian contact information to migrate to Arbor | Split any merged contacts so that each guardian has their own, which will mean they each have their own profile in Arbor
3.2 | Duplicate Guardian Profiles | Ensure there are no duplicate guardian profiles in Bromcom. If a contact is listed on multiple student profiles (e.g. siblings), there will be duplicate guardian profiles migrated over to Arbor. | Duplicate guardian records will impact the use of communications, and in some cases could present a safeguarding risk | Resolve any duplicate guardian profiles in Bromcom. If you can't do this in Bromcom, make a plan to do it in Arbor after Go Live using this guidance - Resolve duplicate students in Arbor
3.3 | Guardian Addresses | Make sure guardian addresses look correct, with the right information in the right field (e.g. Post Codes only in the Post Code field) | Accurate address information will be needed to effectively use Arbor's communication functionality. | Make sure that all information is in the right place (e.g. no street names in the Post Code field), and that addresses are correct.
3.4 | Guardian Phone Numbers | Check guardian contact numbers and ensure that none have non-number characters (International dialling codes and spaces are accepted). | Phone numbers that include a special character (e.g. *) will not be imported. | Remove special characters. If there is more than one phone number in a single field, split them into one field per phone number.
3.5 | Guardian Contact Details | Check that all guardian contact details are stored in the guardian section of the profile, and not as student contact details. How do we migrate guardians and contacts? | Guardian contact details that are stored as Student contact details will migrate to the Student profile, not the guardian profile, so it's important to check this in Bromcom. | Move guardian details to the correct place on the profile.
3.6 | Parental Responsibility Status | Check that each student has a primary guardian with parental responsibility set correctly. Run a report and check the parental responsibility and communications field set correctly. | Guardians with Parental Responsibility will be set as 'Primary Guardians' in Arbor, and will receive communications for that child. This is something that can be changed once Live on Arbor if necessary, however, doing this now will save time once you are Live with Arbor. | Add or remove parental responsibility as required. (e.g. a grandparent may be authorised to collect, but this doesn't mean they have parental responsibility)
3.7 | Historic Guardian Records | Check your school's policy for data retention and delete records that are beyond the retention period | Holding data beyond the retention period is a breach of GDPR, so this will need to be amended in Bromcom before the migration or after the migration in Arbor | Delete the records that you no longer need to keep in line with your Data Retention Policy. If you are unable to delete all historic records before migration, it's easy to do in Arbor afterwards. This guide explains how: Managing data retention in Arbor

## 3.Data Counts
Data Counts
Use this page to help you compare the data in your previous system, to what we have migrated into your new Arbor MIS. Complete the 'Number in Bromcom' column before you migration, and the 'Number in Arbor' column after the migration. You can also use the Data Migration Report you can download from Arbor to help with this. We also have further guidance here. If you notice any discrepancies in the data, please follow the steps in this guide.
Field | What should I count? | Number in Bromcom | Number in Arbor | Checked By | Status
Enrolment | Count of whole school enrolment | e.g 307 | e.g 307 | e.g Joe Bloggs
Count of enrolment by Year Group
Count of enrolment by Registration Form
Demographic | Count of students with FSM status
Count of students with Ever6FSM status
Count of students with Service Child status
Count of students with Pupil Premium eligibility
Count of students with EYPP eligibility
Count of students with Service Child status
SEN | Count of students with SEN Status
Count of Students by SEN Need To check this in Arbor navigate to Students > Educational Needs > Students with SEN > SEN Needs
Staff | Count of staff this academic year To check this in Arbor navigate to School > All Staff > Single Central Record
Attendance | Percentage Present for Academic YTD To check this in Arbor navigate to Students > Attendance > Statistics > Use filter to change date and type
Percentage Absent for Academic YTD To check this in Arbor navigate to Students > Attendance > Statistics > Use filter to change date and type
Percentage Authorised Absent for Academic YTD To check this in Arbor navigate to Students > Attendance > Statistics > Use filter to change date and type
Percentage Unauthorised Absent for Academic YTD To check this in Arbor navigate to Students > Attendance > Statistics > Use filter to change date and type
Student Profiles | Check a random sample of 5 student profiles - check that everything has migrated as expected including Guardian information. The list should include students from the following groups: FSM, In-Care, Service and are from a range of year groups. Search for the student's name in the search box or go to Students > All Students > Browse Students to start checking. Click here and here for FAQ's
Staff Profiles | Check a random sample of 10 staff profiles. Check everything on their profile including DOB, Address, Teacher Number, checks/qualifications, NI numbers etc. Search for the staff name in the search box or go to School > All Staff > Browse Staff
Staff Business Roles & Permissions | Check that all of your staff members Business Roles and Permissions are correct - click here for more guidance

## 4. Training Checklist
Training Checklist
All training is available to book via The Arbor Training Hub
Click here to access The Arbor Training Hub
Use this page to keep track of the training you need to complete. Your Project Lead will automatically be enrolled into the Arbor Training Hub, and have access to all training you have purchased as a school. This includes all of our "Arbor Foundations" training, which every school should complete to ensure they are confident with the basics of Arbor. These courses are listed below. Your Project Lead will also be able to book any additional or bespoke training the school has purchased, such as Meals, Payments or Assessments training for example. To nominate additional users for the Training Hub, please complete the form sent in your Training Email (Week 1)
Teacher Training
Teachers don't normally need access to the Arbor Training Hub - You can share these training videos with them instead - Getting Started and Teacher Essentials
Arbor Foundations Training
You must complete the below courses before you Go Live with Arbor - they are in the "Pre-Go Live" learning path on the Training Hub
Course Name | Description | Course Type | Duration | Status
Getting Started | Aimed at all Arbor MIS users, this course will introduce you to Arbor and explain how to access support, if needed. You will explore the Arbor Navigation menus, how to access and understand your home Dashboard and KPIs, and get top tips from our Customer Education Specialists. | E-Learning Course | 13 mins
Student Profiles and Adding Demographics | Aimed at School Administrators, this course will show users how to navigate and edit Student Profiles, including where additional information, such as SEND and Medical, can be stored and administered. | Live Session | 90 mins
Adding Students and CTFs | Aimed at School Administrators, this course will allow users to manage student Enrolment, including CTFs, ready for day one. | Live Session | 60 mins
Staff Business Roles and Permissions | Aimed at School Administrators, this course will allow you to manage new and existing users and their Business Roles and Permissions effectively in Arbor. | Live Session | 45 mins
Primary Attendance Management | Aimed at Attendance Officers and School Administrators, this course will deep-dive into Arbor's Attendance Module, getting you ready for day one. | Live Session | 90 mins
Attendance Reporting | Aimed at Attendance Officers and School Administrators, this course will give you a deep-dive view of Arbors' Attendance Module's reporting tools. | Live Session | 60 mins
Communications | Aimed at Office Managers and School Administrators, this course will teach you how to set up and manage your school Communications in Arbor. | Live Session | 90 mins
You can complete the below courses after you Go Live with Arbor if you wish, they are in the "Post Go-Live" learning path in the Training Hub
Course Name | Description | Course Type | Duration | Status
Guardian Profiles | Aimed at School Administrators this course will show users how to add and manage Guardian information. We recommend completing the Student Profiles course before starting this course. | E-Learning Course | 45 mins
Staff Profiles | Aimed at School Administrators, this course will allow users to add, find, edit and navigate Staff Profiles. | Live Session | 60 mins
Staff Absence and Cover | Aimed at Office Administrators and Cover Managers this course will show users how to record and report on Staff Absence, set Cover, and manage Supply. | Live Session | 60 mins
Arbor MIS Management | Aimed at Office Administrators and Cover Managers this course will show users how to record and report on Staff Absence, set Cover, and manage Supply. | E-Learning Course | 15 mins
Single Central Record | Aimed at School Administrators, this course shows users how the Single Central Record can be stored in Arbor. | E-Learning Course | 15 mins
Staff Contracts and Payscales | Aimed at Administrators and HR staff, this session will show users how to add Employment and Financial information including Contracts, Checks, Pay Scales, Positions, Allowances, and Superannuation Schemes. | Live Session | 75 mins
Custom Groups | Aimed at Data Managers and School Administrators, this course will teach you how to create, manage and use Custom Groups in Arbor. | E-Learning Course | 15 mins
User Defined Fields | Aimed at Data Managers and School Administrators, this course will teach you how to create and manage User-Defined Fields in Arbor. | E-Learning Course | 10 mins
School Reporting | Aimed at Senior Leaders, Business and Data Managers, this course will teach you where to find and use the in-built analysis tools, helping you locate key School Statistics. | E-Learning Course | 20 mins
Custom Report Writer | Aimed at all Staff who would like to learn how to use the in-built Custom Report Writer features to build bespoke reports. | Live Session | 75 mins
Arbor AI Overview | This course, aimed at Project Leads and School Administrators, will introduce you to Arbor AI, its features, and how to manage them. | E-Learning Course | 10 mins
Arbor AI Modules | Aimed at all MIS users, this course will introduce you to the Arbor AI features in the available modules. | E-Learning Course | 20 mins
More Information: Click here to see our Training Schedule
Please Note: You will find the resources/recordings from the live sessions in the "Primary Onboarding Resource Library" course on your Dashboard in the Training Hub
Additional and Bespoke Training
You may have purchased some additional training to help get you up and running with modules such as Meals and Payments in Arbor. You may also have purchased Bespoke Training such as Assessment or Behaviour Training. Any additional training will automatically be added to the Project Lead's Training Hub account. If you would like to discuss purchasing any of the additional training listed below, please contact customersales@arbor-education.com
Additional Training (Meals/Payments/Parent App)
Course Name | Description | Course Type | Duration | Status
Arbor Foundations: Meals Setup and Management | Aimed at School Administrators and Office Managers, this course will teach you how to setup and manage your Meals offering in Arbor. | Live Session | 90 mins
Arbor Foundations: Payments Setup and Management | Aimed at Business Managers and/or Finance Managers, this course will guide you through setting up your system for card payments and managing your accounts and balances. | Live Session | 90 mins
Arbor Foundations: Parental Engagement | Aimed at School Administrators and Office Managers, this course will show you how to set up and use the Parent App and Parent Portal to manage your communication and engagement with Parents and Guardians. | E-Learning & Live Sessions | 3 hours
Arbor Foundations: Payments Plus | Aimed at School Administrators and Office Managers, this course will teach you how to setup and create your rotating meal menus to allow your parents to select their child's meal choices from the parent portal. | Live Session | 45 mins
Bespoke Training (Assessments/Behaviour/Reporting)
Course Name | Description | Course Type | Duration | Status
Behaviour Consultation and Reporting | Aimed at Behaviour Leads, this consultative course will show you how to set up and manage behaviour in Arbor based on your requirements. | Click here for more info | Click here for more info
Assessment Consultation | Aimed at the Assessment Lead/decision maker - you'll discuss how you'd like to manage your assessments in Arbor. | Click here for more info | Click here for more info
Operational Reporting | Aimed at Headteachers and Senior Leaders, this session will teach you how to report on key areas in Arbor. | Click here for more info | Click here for more info
More Information: How to book 1-1 sessions
Training Test Site
You can put what you have learnt in your training sessions to the test, using our Arbor Training Test Site - this is a real Arbor system with test data pre-loaded into the system. It looks and works the same as a real Arbor MIS, so is the perfect way to familiarise yourself with Arbor ahead of your migration and Go Live. The link to access the site, as well as long in details can be found in your week 1 email.