## Key Onboarding Milestones
Welcome to Arbor
Over the 8 weeks, you will use this workbook to help you set up your new Arbor MIS! Each page is designed to help you keep track of the onboarding project and provide information and training on how to set your Arbor site up.
Key Onboarding Milestones
This tab contains an overview of the tasks you will complete during your 8 week onboarding journey and when you should do them. You should update this regularly to help you keep track of your progress. | ✔ | = Complete
| ✖ | = Delayed
| ▲ | = In Progress
Milestone | Status | Due | Owner
Watch 'Welcome to your Onboarding' video | ✔ | Week 1 | School Project Lead
Blank Arbor site released | ✔ | Week 1 | Arbor Onboarding Team
Log into blank Arbor site | ✔ | Week 1 | School Project Lead
Watch Site Setup Training Module 1 (School Details and Pastoral Structure) | ✔ | Week 1 | School Project Lead
Add School Details and Pastoral Structure to Arbor site | ▲ | Week 1 | School Project Lead
Watch Site Setup Training Module 2 (Adding and Enrolling Students) |  | Week 2 | School Project Lead
Add Student Enrolment data to Arbor site |  | Week 2 | School Project Lead
Watch Site Setup Training Module 4 & 5 (4. Managing Student Profiles & 5. Managing Guardian Profiles) |  | Week 2 | School Project Lead
Add Student Profiles and Guardian Profiles data to Arbor site |  | Week 2 | School Project Lead
Book your Onboarding Training | ✖ | Week 2 | School Project Lead
Contact any 3rd party apps and information them of your move to Arbor |  | Week 2 | School Project Lead
Inform your team of the move to Arbor |  | Week 2 | School Project Lead
Watch Site Setup Training Module 6 and 8 (6. Managing Staff Profiles and 6. Managing Staff Absences) |  | Week 3 | School Project Lead
Add Staff Profiles and Absences data to Arbor site |  | Week 3 | School Project Lead
Attend your Onboarding training |  | Week 3 | School Project Lead
Watch Site Setup Training Modules 9 (9. Contracts & Payscales) |  | Week 4 | School Project Lead
Add Staff HR and Admin data to Arbor site |  | Week 4 | School Project Lead
Check readiness for Go Live |  | Week 4 | School Project Lead
School entered all necessary data ready for Day 1 |  | Week 4 | School Project Lead
Ensure all staff can log into Arbor |  | Week 5 | School Project Lead
Go live and start using Arbor for taking attendance |  | Week 5 | School Project Lead
Connect any required 3rd party apps to your Arbor system |  | Week 5 | School Project Lead
Attend your Post Launch Onboarding Arbor Academy training |  | Week 6 | School Project Lead
Check in with staff, ensure all are aware of support options etc |  | Week 7 | School Project Lead
Complete any outstanding training |  | Week 8 | School Project Lead
Handover to Customer Success Team |  | Week 8 | Arbor Onboarding Team

## Set Up Overview
Site Setup Overview & Training
Included in this tab are your all important site setup training videos! There are 5 parts to watch in total, and following on from each session you should add the relevant data into your blank Arbor site. You should use this tab to keep track of your progress. Please note: It may be that some of this information is not relevant for you or does not need to be added to your Arbor site, for example if you are not using Arbor to manage staff HR/Contracts, you won't need to add this into Arbor. To access the training videos please click on the green text below.
Site Setup Training | Training Videos | Owner | When to watch video | When to enter data into Arbor
Part 1: School Details and Pastoral Structure (21 mins) | Creating your Academic Year (5 mins) | School | Week 1 | By end of week 1
Checking your school details (4 mins)
Adding Staff Manually (3 mins)
Importing Staff Profiles in bulk (2 mins)
Creating your Pastoral Structure (4 mins)
Scheduling Registration Sessions - Primary (3 mins)
Part 2: Student Enrolment / Adding Students into Arbor (18 mins) | Adding Students Manually or via CTF (5 mins) | School | Week 2 | By end of week 2
Creating an Intake Season (3 mins)
Adding Students via the Applicants Module (10 mins)
Part 3: Student and Guardian Profiles (64 mins) | Finding a Student profile (3 mins) | School | Week 2 | By end of week 2
Student Profile overview Part 1 (8 mins)
Student Profile overview Part 2 (21 mins)
Student Profile overview Part 3 (11 mins)
Creating a Guardian Profile (4 mins)
Finding a Guardian Profile (3 mins)
Linking a Guardian with a student (2 mins)
Guardian Profile Overview (12 mins)
Part 4: Staff Profiles and Absences (31 mins) | Finding a Staff Profile and Overview (10 mins) | School | Week 3 | By end of week 3
Overview of Business roles and permissions (6 mins)
Adding and Editing Basic information (6 mins)
Logging Staff Absences (7 mins)
Staff Absence Statistics (2 mins)
Video 5: Staff Contract and Payscales / HR Admin (31 mins) | Creating Allowances (2 mins) | School | Week 4 | By end of week 4
Checks (5 mins)
Payscales (5 mins)
Positions (5 mins)
Superannuation schemes (2 mins)
Creating Staff Contracts (12 mins)
School Details and Pastoral Structure | Owner | Training Video | Progress
Term Dates | School | Video 1
Holidays | School | Video 1
Year Groups | School | Video 1
Registration Forms | School | Video 1
Houses | School | Video 1
Student Information | Owner | Training Video | Progress
Add students by CTF or Applicant Import Spreadsheet | School | Video 2
Add Student enrolment information | School | Video 2
Funded Hours/ Hours at Setting/ Extended Entitlement Hours Information | School | Video 3
Disability Access Fund Indicator | School | Video 3
Early Years Pupil Premium Recipient Indicator | School | Video 3
Top up Fund Indicator | School | Video 3
Post Looked After Arrangements | School | Video 3
Medical Conditions | School | Video 3
Dietary Requirements | School | Video 3
Consents (Not required for census) | School | Video 3
Pastoral notes, linked documents (Not required for census) | School | Video 3
Guardian Information | Owner | Training Video | Progress
Add Guardian information | School | Video 3
Add Guardian contact details | School | Video 3
Staff Information | Owner | Training Video | Progress
Staff Details | School | Video 4
Teacher/ TA status | School | Video 4
Other staff data, including disability etc. | School | Video 4
Qualifications | School | Video 5
Payscales | School | Video 5

## Setup Overview (Improved) (hidden)
Data
Included in this tab is a list of all the important data that you will need to add to your Arbor site in readiness to take attendance on day 1! As part of your training, (available to access in the Arbor Training Hub - Brand New School Site Setup Training) you will go through short snippet videos that will go through how to add your key data to your Arbor site. Following each video, you should then add your data to your site using this tab to keep track of your progress. Please note: It may be that some of this information is not relevant for you or does not need to be added to your Arbor site, for example, if you are not using Arbor to manage staff HR/Contracts, you won't need to add this into Arbor.
Data to add to your Arbor site:
| School Details and Pastoral Structure | Progress | Owner | Due Date
| Term Dates |  | School
| Holidays |  | School
| Year Groups |  | School
| Registration Forms |  | School
| Houses |  | School
| Student Information | Progress | Owner | Due Date
| Add students by CTF or Applicant Import Spreadsheet |  | School
| Add Student enrolment information |  | School
| Funded Hours/ Hours at Setting/ Extended Entitlement Hours Information |  | School
| Disability Access Fund Indicator |  | School
| Early Years Pupil Premium Recipient Indicator |  | School
| Top up Fund Indicator |  | School
| Post Looked After Arrangements |  | School
| Medical Conditions |  | School
| Dietary Requirements |  | School
| Consents (Not required for census) |  | School
| Pastoral notes, linked documents (Not required for census) |  | School
| Guardian Information | Progress | Owner | Due Date
| Add Guardian information |  | School
| Add Guardian contact details |  | School
| Staff Information | Progress | Owner | Due Date
| Staff Details |  | School
| Teacher/ TA status |  | School
| Other staff data, including disability etc. |  | School
| Qualifications |  | School
| Payscales |  | School

## Key Documents & Help Guides
Key Documents & Help Guides
This tab includes a number of useful Help Centre articles/areas to assist you with your onboarding, ranging from hints and tips to get your onbording off to the best possible start, to a module-by-module breakdown of getting the most out of your new Arbor MIS! If you can’t quite find what you are looking for, or if you need any further support (if you are not partner supported) please contact our Support Team using one of the options here: Contact Us
Webchat via the Help Centre or within your Arbor site
Logging into Arbor | How to get your whole team logged in and troubleshoot any logging in issues
Teacher Guide | Introduction to Arbor for Teaching Staff
Admin Guide | Introduction to Arbor for Admin Staff
Attendance Officer Guide | Introduction to Arbor for Attendance Officers
Arbor Help Centre by Module
3rd Party Integration Help | Staff Profiles, Access and HR
Attendance | Custom Report Writer
Communications

## 3rd Party Apps Systems Audit
3rd Party Applications Systems Audit
Making sure that third party systems are connected to your MIS is key to a successful Go Live. This Systems Audit will help you to identify the systems you're using and keep track of when you have integrated these with Arbor. Click here for more information on the applications we integrate with and click here to find out how to connect with them.
Application Name | Notifed of move to Arbor? | Connection Status | Additional Notes
e.g, CPOMS | Yes | Pending | Kate to connect on Go Live day
e.g InVentry | Awaiting Response | Delayed | Beth to chase

## Third Party System Audit (hidden)
System Audit
We can integrate with Third Party Applications in three ways:
1. Manual sync from Arbor |  | For Applications that do not offer an automated integration, Arbor can help you to keep your application updated by uploading a report. Please see column 'Additional Notes & next steps' for the link to the help centre to show you how to integrate with each application where a manual sync is required. We will update the links for you when your third parties have been listed. NOTE: You will need to contact your Application Provider to let them know of your move to Arbor!
2. Direct Arbor API |  | Some companies choose to integrate directly with Arbor's API, others choose to do this via a company such as Groupcall or Wonde. If the integration listed in the 'solution' column is either 'Arbor API' or 'Third Party API', the method of connecting for the school is the same. Please click here for instructions on how to connect. Note: Either the school or the Trust (depending on who's managing the integrations in your programme) will need to contact the application provider directly and inform them of your move to Arbor. They will advise you further on the next steps from their end.
3. Third Party API
List all of the applications that your schools currently use:
Application Name | Provideer | Replace with Arbor? | When do you plan to replace? | What does the application do? | School(s) | Cost of Application | Appliation Renewal Date | Sync Status | Solution | Owner | Notified Application of Move to Arbor? | Go Live Date for integration | Additional Notes and Next Steps
e.g. CPOMS |  | No Replacement | e.g. School Go Live, December 19 etc. | e.g. Safeguarding |  | e.g. £0.00 | e.g. 01/04/2020 | Pending | Arbor API | e.g. School | ✓ Yes | e.g. 10/10/2017 | e.g. School required day one
[8 empty] | Pending | Manual Integration |  |  |  | Full Help Centre Guide
[8 empty] | Pending | Third party API |  |  |  | Full Help Centre Guide
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending

## Trust Implementation Plan & Tim (hidden)
Trust Timeline Plan
| Aims | Status | Owner | Milestones | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Discover & Plan
| Handover to implementation |  | Arbor Programme Lead | • MAT Kick Off • MAT Discovery • Implementation & Shared Success Plans • Coordinated Training Plans • Plan for third party applications • Fornightly Progress Calls | bar: Week 1
| Complete Kick Off Call |  | Arbor Programme Lead & MAT Team | bar: Week 1
| Complete MAT discovery day & needs requirement, including trusts approach to trust & school alignment |  | Arbor Programme Lead & MAT Team
| Identify roles & responsibilities & plan for risk management |  | Arbor Programme Lead & MAT Team
| Identify phase 1 schools and Arbor Champions |  | MAT Team
| Confirm MAT and school implementation plan and objectives |  | Arbor Programme Lead & MAT Team
| Training needs analysis for teaching and support staff & confirm training plan for schools |  | Arbor Programme Lead & MAT Team
| School/ MAT contacts all third party integrations prior to go live |  | School Team & MAT Team
| Commence Fortnightly Progress Calls |  | Arbor Programme Lead & MAT Team
| Communicate roll out plan & training plans to schools |  | MAT Team
| School Implementation Kicks Off |  | Arbor Programme Team & MAT Team
Deployment
| Schools complete Arbor pre launch implementation |  | School Team | • Data Checks & Counts • Training • Data Migration • School Go Lives • Weekly School Project Progress Calls • Fortnightly MAT Project Progress Calls • Performance Reporting | bar: Week 1
| Schools complete Arbor training |  | School Team | bar: Week 1 to Week 2
| Schools complete data checks & counts |  | School Team | bar: Week 1
| School/ MAT completes final data migration |  | School Team & MAT Team | bar: Week 1
| Arbor releases school sites |  | Arbor Programme Team | bar: Week 4
| School signs off data migration report |  | School Team | bar: Week 4
| Commence schools weekly project progress calls |  | Arbor Programme Team & School Team | bar: Week 4
| Coordination of service packages |  | Arbor Programme Team & MAT Team | bar: Week 4
| Onsite Half Term Performance Reporting |  | Arbor Programme Lead & MAT Team | bar: Week 6 to Week 7
Growth
| Continued delivery of service packages & training |  | Arbor Programme Team & MAT Team | • Final Review • Graduation
| Adoption of best practice with the support of the Arbor community |  | School Team
School Graduation
Final review of programme success, performance & impact reporting
Trust Graduation

## Training Plan (hidden)
MAT Training Plan
Here we will keep a handy list of all of your proposed, booked and completed training sessions:
Please note that online training sessions will have additional breaks if longer than one hour, so three hours of online training will require 3.5 hours of total training time allocated.
Purchased Training | Is the session split? | Who is the training for? | Agenda | Booked date/time | Link to attend training | Status | Notes | Logged on GS? (Arbor Internal)
1 x InPerson Primary PreLaunch training : School Ops | Part 1 | MAT central team | Click here for agenda |  |  |  |  | FALSE
| Part 2 | MAT central team
Online Primary Post Launch Training : School Ops | Part 1 |  | Click here for agenda |  |  |  |  | FALSE
Part 2
In-Person Assessment Consultation (Half Day) | Part 1 |  | Click here for agenda
| Part 2 | [6 empty] | FALSE
In-Person Assessment Setup Training (Half day) | Part 1 |  | Click here for agenda |  |  |  |  | FALSE
Part 2
In-Person Assessment Analysis Training (Half day) | Part 1 |  | Click here for agenda
Part 2
School Payments | 1/2 day |  | Click here for agenda
School Meals | 1/2 day |  | Click here for agenda
Online Group MIS Training |  |  | Click here for agenda

## School Site Setup Agenda (hidden)
Session | Details | Time
New School Site Setup 1: School Details and Pastoral Structure | This session covers the following topics: •Setting up School Details •Creating previous Academic Calendars •Adding Staff Profiles •Setting and checking Business roles & Permissions •Setting up last year's Pastoral Structure (Year Groups and Reg Forms) | 60 mins
New School Site Setup 2: Student Enrolment | This Session covers the following topics: •Creating an Intake Season •Adding students to Intake Season via CTF or manually •Enrolling Applicants (students) •Amending student start dates •Managing School Leavers | 60 mins
Student Profiles and Guardian Profiles | This session covers the following topics: •Navigating Student Profiles •Adding and Amending Data on a Student Profile (inlcuding information required for first school census) •Adding Exclusions •Adding and accessing Guardian Profiles •Bulk updating Guardian Profiles ( Contact details, Authorised to Collect) •Editing Guardian Profiles (including Student/Guardian relationships (Primary/Legal status)) | 1hr 30 mins
Staff Profiles and Absences | This session covers the following topics: •Navigating Staff Profiles •Adding and amending data on a Staff Profile •Logging Staff Absences •Reporting on Staff Absences | 60 mins
Staff HR and Admin | This sessions covers the following topics: •Adding and amending Staff Contracts •Managing Positions •Managing Payscales and Allowances •Ending staff employment | 60 mins

## Data Migration & School Details (hidden)
Data Migration
School Name | Current System | Phase | Link to school's implementation workbook | Last day of term | Go Live Date | Kick off call booked? | Kick off call complete? | Arbor Secure Portal for back ups to be sent | Data Uploaded | Site Released
| SIMS | Special |  |  |  | FALSE | FALSE |  | FALSE | FALSE
| SIMS | Secondary |  |  |  | TRUE | TRUE |  | FALSE | FALSE
| SIMS | Primary |  |  |  | FALSE | FALSE |  | FALSE | FALSE
| SIMS | Special |  |  |  | FALSE | FALSE |  | FALSE | FALSE
| N/A |  |  |  |  | FALSE | FALSE |  | FALSE | FALSE
| N/A |  |  |  |  | FALSE | FALSE |  | FALSE | FALSE
| N/A |  |  |  |  | FALSE | FALSE |  | FALSE | FALSE
| N/A |  |  |  |  | FALSE | FALSE |  | FALSE | FALSE
Click here to view our full help centre article on sending your SIMS back up

## Readiness for Go-Live Checklist
Readiness for Go-Live Checklist
This tab will act as a checklist for you and your school to ensure that you've completed key tasks in the run-up to going live with the Arbor MIS. Here you can find useful information to help you, and tick-off tasks to make sure your first day with Arbor is a success!
Readiness for Go Live Task | Task Complete?
Complete 5 x Site Set Up Training Videos (detailed in the 'Set Up Training & Overview' tab) | FALSE
Add all necessary information to Arbor site: - Year Groups and Registration Forms - Term Dates and Holidays - Student Enrolment - Student Data - Guardian Data - Staff Data | FALSE
Make sure users have the correct Business Roles & Permissions (use this guide as help) | FALSE
Ensure all staff have their work email address set as their 'default' email address to make sure they can get logged in | FALSE
Share your URL with your wider team ready for day 1 along with this helpful guide on how to log in for the first time | FALSE
Ensure all required 3rd party applications/providers are ready to connect | FALSE
Confirm that your registers are available for Day 1 (Students > Attendance > Registers by Date) | FALSE
Ensure staff are trained up and confident in their area (you can use this admin staff guide and teachers guide) | FALSE
Make sure teachers know how to take a register on day 1 (provide teachers with this guide) | FALSE
Helpful guides to help you prepare for Go-Live
Teachers Guide
Admin Guide
Readiness for Go Live Checklist