## 1. Onboarding Checklist
Weekly Onboarding Checklist
Welcome to Arbor, we're excited to have you onboard! Use this workbook to keep track of the key tasks you need to complete over the next 8 weeks as you transition to Arbor. Please review each tab of the workbook carefully as this has everything you'll need to action for a successful move.
Week 1 | Status
1. Watch your Introduction Video - you can find this in your Week 1 email or click here to watch | FALSE
2. Complete the form in your Training Email to register additional users for the Training Hub - Click Here for more info | FALSE
3. Log in to the Arbor Training Hub and start your training. Use tab 4. Training in this workbook to track your progress | FALSE
4. Review our help centre guidance here, to see what does/doesn't migrate via Groupcall, as well as our Common Migration FAQs | FALSE
5. Review our guidance on how to add additional data to your Arbor site post migration | FALSE
6. Review our Groupcall Migration Pre Requisites to ensure your SIMS server is ready for the Migration | FALSE
7. You'll receive access to your Arbor Secure Upload Portal in Week 1 - you'll need to log into this to accept our T&Cs so that we can start your migration on the agreed date | FALSE
Week 2 | Status
1. Begin your Pre-migration Data Cleansing and Counts using tab 2. Pre-Migration Data Cleansing and 3. Data Counts of this workbook | FALSE
2. Look out for your Secure Upload Portal - let us know if you don't receive this by emailing myonboarding@arbor-education.com | FALSE
3. Accept the Arbor Terms and Conditions via the Arbor Secure Upload Portal - Migrating to Arbor using Groupcall Xporter on Demand | FALSE
4. Provide Groupcall with Authorisation to share your data with Arbor - Follow the steps in this guide | FALSE
5. Install Groupcall Xporter on Demand Application if you don't already have this installed | FALSE
6. Ensure the user that has approved GroupCall data sharing request has access to all these key areas of SIMS - Check this guidance for more information on permissions | FALSE
7. Contact your 3rd parties and let them know you're moving to Arbor - Guide to third party APIs | FALSE
Week 3 | Status
1. Complete your Pre-migration Data Cleansing by the end of this week (tab 2. Pre-Migration Data Cleansing will help you with this) | FALSE
2. Continue to complete your Arbor Foundation training, (you can use Tab 4. Training Checklist in this workbook to track progress) | FALSE
3. Share this Teacher Essentials Training so that your teaching staff know how to take attendance in Arbor when you go live | FALSE
4. Review Tab 5 (Important Checks for Migration) of this workbook to ensure you're setup for migration | FALSE
5. Ensure you have a plan to keep a copy of your data for your Data Retention Purposes (you do not need to send this to Arbor) | FALSE
Week 4 - Migration Week! | Status
1. Continue to complete your Arbor Foundation Training, (you can use Tab 4. Training Checklist in this workbook to track progress) | FALSE
2. Complete data counts using tab 3. Data Counts in this workbook | FALSE
3. Ensure all previous steps have been completed as this week your migration to Arbor begins! | FALSE
4. IMPORTANT: Leave your SIMS server on and ensure it remains on - Arbor can only access your data when the server is online | FALSE
Week 5 - Go Live Week! | Status
1. Log in to your new Arbor site and read our Getting Started guide to help you get going! | FALSE
2. Share your Arbor URL with the rest of your team so they can log in - click here for our login issues troubleshooting guide | FALSE
3. Share our "Getting Started with Arbor" help centre guidance with your team | FALSE
4. Start taking attendance in Arbor! | FALSE
5. Download and review your Data Migration Report - use this to help check the data in Arbor and sign this off when you're happy with the data on Arbor following migration | FALSE
Week 6 | Status
1. Finalise all of your data checks in Arbor and sign off your data migration report | FALSE
2. Raise any data migration issues with Support - Please note if you are a partner supported school, you will need to raise migration issues with your Support Partner | FALSE
3. Switch Groupcall from SIMS to Arbor only if you have carefully checked the data in Arbor, as once switched this cannot be switched back. Click here for more information. | FALSE
4. Approve any 3rd party connections in Arbor | FALSE
5. Familiarise yourself with how to contact support for any 'how to' questions | FALSE
Weeks 7 & 8 | Status
1. Complete any outstanding Arbor Foundations Training | FALSE
2. Make sure you've signed up to Arbor HQ! | FALSE
At the end of week 8, your onboarding is complete! If you have Arbor Support, our Customer Success Team will work with you from this point onwards to ensure long term success on Arbor. If you are supported by a Partner, your partner will continue to work with you moving forward.

## 2. Pre-Migration Data Cleansing
Pre Migration Data Cleansing
We've prepared these data checks and cleansing tasks for you to complete in your current MIS. They will help to make sure that the data we import to your new Arbor system is as accurate as is possible. You must complete the data cleansing by the end of Week 3 of your onboarding journey.
Ref | Field | What should I check? | Why do I need to check this? | How do I clean it up? | Status
Staff Data
1.1 | Staff Email | Check that staff have a work email address on their staff profile. | This will become their Arbor username. Staff will not be able to log in to Arbor without an email address. Click here for more information on how we migrate email addresses. | Add a work email address to their profile. This will need to be set as main and primary.
1.2 |  | Check that all staff emails are accurate and do not have any typos or errors . | This will become their Arbor username. Staff will not be able to log in to Arbor without an email address. | Amend any errors
1.3 |  | Check that staff work email address are only used once in your current MIS. i.e. Any staff members who have guardian profiles at the school must have a personal email only on their guardian profile. *Important to note for SIMS users* For your staff members that are also guardians please ignore the above - if there are staff email addresses on the guardian section (section 5 family and home) removing the staff email address from section 5 may simultaneously remove it from the staff profile. This will migrate over to Arbor and cause login issues for the staff members that are also guardians - you will be able to see the staff members with this issue and easily fix it with the help of this guide. | If staff email appears on a guardian profile following migration, that staff member will not be able to log in to Arbor until it is removed. | Make sure that all information is in the right place (e.g. no street names in the Post Code field), and that addresses are correct. Make sure historic addresses have an end date
1.4 | Staff Contracts | Check that any old staff contracts and roles have an end date. | If historic staff do not have an end date on their contract and role, they will migrate as active staff members, and you'll need to delete them from Arbor. Click here for information on what to do in Arbor if this happens and old staff members have migrated as current staff | Add end dates to all contracts and roles
1.5 |  | Ensure all current staff have an active business role and a current contract | Staff must have an active business role and contract to be able to log on. Contracts/Business Roles must be up to date and reflect the staff members current role e.g. if a teaching assistant is now a teacher, but their contract hasn't been updated they will migrate with a TA role. Click here for more information on how we migrate this.
1.6 | Duplicate Staff | Run a report on staff to identify duplicates | Duplicate staff records will prevent staff from logging into Arbor. | Resolve any duplicates. If you can't do this in your current MIS, make a plan to do it in Arbor after Go Live using this guidance
1.7 | Phone Numbers | Run a report on staff contact numbers and check that none have non-number characters (International dialling codes and spaces are accepted). | Phone numbers that include a special character (e.g. *) will not be imported. Click here fore more information on how we migrate phone numbers. | Remove special characters. If there is more than one phone number in a single field, split them into one field per phone number.
1.8 | Next of Kin | Check staff Next of Kin has correct information | Due to the migration, Next of Kin are migrated, but a separate account is created as a duplicate. These can be deleted from Arbor, without removing them from the staff profile. Click here for more information on how we migrate Next of Kin. | Ensure information is correct and up to date
1.9 | Welsh Identification Fields (only applicable for Welsh Schools) | Check that data is correct for Welsh-specific migration fields: - Teacher number 7 digits: a unique Teacher Reference number known as the EWC number, for members of staff who have one, this is a unique identifier - Disability code - Qualified Teacher Date: date of qualification, compulsory for all teachers - Is NPQH: National Professional Qualification for Headship (applies to any member of staff) - NPQH Date: date National Professional Qualification for Headship acquired - Welsh Teaching Ability Code: ability to teach in Welsh - Welsh Teaching Code: status of teaching in Welsh - Long-Term Absence Status Code: identify individuals who are on long-term absences: maternity, secondment - EYT Status - Welsh Ability - HLTA Status | To ensure this data migrates to Arbor as expected | Ensure information is correct and up to date
1.1 | Staff Leaver Retention Details (only applicable for Welsh Schools) | The School Workforce Annual Census (SWAC) collects data on staff retention, particularly focusing on teachers who have left their positions during the previous academic year. The SWAC aims to understand staffing trends in Welsh schools and inform policy decisions by tracking information such as reasons for leaving and the leavers' destinations. | This will be captured for most Teachers (excluding some supply/trainee), Teaching Assistants Special needs support staff | If this is stored in SIMS please check this data is correct for migration
1.11 | Third Party (Welsh Schools) | Check that staff who are not directly employed by the local authority are correct in SIMS
Student Data
2.1 | Demographics (Pupil Premium Eligibility) | Check that FSM eligibility is set correctly, with a start and end date (if applicable) | Arbor derives PP eligibility based on the eligibilty criteria. We do not have a PP tick box like some MIS. If there is no underlying eligibility criteria, students will not show as PP eligible. If no end date is recorded for these criteria, they will show as Ongoing Click here for more information | Make sure that any relevant demographic criteria has a start and an end date
2.2 |  | Check that Ever6FSM eligibility is set correctly, with a start and end date (if applicable)
2.3 |  | Check that In Care / Care Leaver status is set correctly, with a start and end date (if applicable) How we migrate LAC
2.4 |  | Check that Service Child status is set correctly, with a start and end date (if applicable) How we migrate this information
2.5 | Medical Information | Confirm students have a relevant Medical Condition added | To ensure students have correct medical condition Click here for more information on how this data migrates | Check/amend/update in SIMS
2.6 | SEN Students (ALN Students for Welsh Schools) | Check that SEN/ALN status is set correctly, with a start and end date (if applicable) | If a SEN/ALN Status has an end date that has passed, the student will not appear as SEN in Arbor, if they don't have an end date they will show as Ongoing in Arbor | In SIMS, this will appear in the Status History. Make sure that all SEN/ALN students have correct start and end dates on their SEN Status, Categories and Needs Some SEN/ALN needs have an end date which are not visable at a glance in SIMS, which means the need does not migrate to Arbor. In SIMS SEN/ALN section, select "Status History" to check the SEN/ALN status does not have an end date
2.7 |  | Check that SEN/ALN Categories and Needs are set correctly, with a start and end date (if applicable)
2.8 | Duplicate Students | Run a report on enrolled students and applicants to identify duplicates. | Duplicate students will impact your number on roll, statutory returns and could present a safeguarding risk | Resolve any duplicates. If you can't do this in your current MIS, make a plan to do it in Arbor after Go Live.
2.9 | Addresses | Run a report on student addresses and check that they look correct, with the right information in the right field (e.g. Post Codes only in the Post Code field) | Accurate address information will be needed to effectively use Arbor's communication functionality. Click here to see how we migrate this information | Make sure that all information is in the right place (e.g. no street names in the Post Code field), and that addresses are correct. Make sure historic addresses have an end date
2.1 | Parent Email/Phone Number | In SIMS, check that parent contact details (email, phone number) are not in section 4 of the student profile. | Parent contact details should be in section 5 of SIMS to ensure they migrate across to the correct place in Arbor. | Ensure you delete any parent contact details from section 4 of SIMS, as other wise the parent details will migrate to Arbor as the students personal email/phone number
2.11 | National Identity (Welsh Schools) | Check that your students have a national identity in SIMS | Schools are required to have this information for PLASC
2.12 | Welsh Specific Fields | Check that data is correct for Welsh-specific student fields: - First Language Source Code: data for the person providing the student's language usage information - Is From Non-English Welsh Systems: boolean field for students joining from non-English and Welsh-based education systems (sometimes called NEWBES) - Arrival from Non-English Welsh Systems Date: date field for students joining from non-English and Welsh-based education systems (sometimes called NEWBES) - Speak Welsh Code: how well does the student speak Welsh - Home Welsh Code: how much Welsh does the student use at home - Welsh Source Code: who has provided the Welsh usage information - Welsh Studied Level Code - Is Other Subjects Studied in Welsh: boolean indicating if other subjects are studied in Welsh - IS FSM Transitional Protection: new boolean field to record where students have acquired FSM (free school meal) transitional protection that will remain with them in their current phase of school regardless of any other circumstances - Is UPFSM Eligible: boolean field recording Universal Primary Free School Meal Eligibility - Is UPFSM Exception: boolean field recording Universal Primary Free School Meal Exception - Grounds for removal - Home LA - Ethnicity Source - EAL Date of assessment - YSSA - IsTraveller - ServiceChild - YoungCarerEndDate - YoungCarerStartDate | Schools are required to have this information for PLASC
Guardian Data
3.1 | Guardian Records | Check that each guardian has their own record (e.g. Mr & Mrs Smith should be 2 separate records) | Needed for accurate guardian contact information to migrate to Arbor | Split any merged records so that each guardian has their own
3.2 | Duplicate Guardians | Run a report on guardians to identify duplicates. | Duplicate guardian records will impact the use of communications, and in some cases could present a safeguarding risk | Resolve any duplicates. If you can't do this in your current MIS, make a plan to do it in Arbor after Go Live.
3.3 | Addresses | Run a report on guardian addresses and check that they look correct, with the right information in the right field (e.g. Post Codes only in the Post Code field) | Accurate address information will be needed to effectively use Arbor's communication functionality. | Make sure that all information is in the right place (e.g. no street names in the Post Code field), and that addresses are correct. Make sure historic addresses have an end date
3.4 | Phone Numbers | Run a report on guardian contact numbers and check that none have non-number characters (International dialling codes and spaces are accepted). | Phone numbers that include a special character (e.g. *) will not be imported. | Remove special characters. If there is more than one phone number in a single field, split them into one field per phone number.
3.5 | Guardian Contact Details | Check that all guardian contact details are stored in the guardian section of the profile, and not as student contact details. How do we migrate guardians and contacts? | Guardian contact details that are stored as Student contact details will migrate to the Student profile, not the guardian profile. | Move guardian details to the correct place on the profile. For example, SIMS users should ensure guardian contact details are stored in section 5 "Family and Home"
3.6 | Parental Responsibility status | Check that each student has a primary guardian with parental responsibility set correctly. Run a report on legal guardians and check the parental responsibility and communications field set correctly | Guardians with Parental Responsibility will be set as 'Primary Guardians' in Arbor, and will receive communications for that child. If this is inaccurate, there may be a safeguarding risk. *SIMS priority' migrates as follows: SIMS priority 1 = Primary guardian in Arbor. SIMS marked as either parental responsibility, receiving correspondence, or the pupil report, or a copy of the bills AND they are not marked as having a court order = Primary guardian in Arbor. Primary guardians are important in Arbor as this is linked with the communications module and usually you can only send all communications to ""primary guardians only"". This is something that can be changed once Live on Arbor if necessary, however, doing this now will save time once you are Live with Arbor | Add or remove parental responsibility as required. (e.g. a grandparent may be authorised to collect, but this doesn't mean they have parental responsibility).
3.7 | Guardians without Linked Students | Run a report on guardians, and check that there are no guardians without a linked student | Guardians with no linked students will need to be deleted, as it's unlikely you have a basis for holding the data. | Link guardians to a student, or delete the records. If you're not able to do this in your current MIS, you can do it in Arbor after go live.
3.8 | Court Orders | Compile a list of Guardians with court orders | Court orders do not migrate, with a list ready these can then be added in to Arbor on your live site
School Data Cleansing
4.1 | Cymru Academic Units | Welsh PLASC census requires some additional class information, these are used for funding, these are for the Class Category, for reporting if the Welsh Language is used in Class and if the class has been designated as a Special Class by the LEA
4.2 | Holidays | Check that your holidays are set up correctly with no overlapping dates or duplicate entries for the same holiday. Make sure there are three terms on the Academic Calendar. Make sure all days are accounted for and there are no gaps in your calendar. | We use your holiday structure to determine academic year start and end in Arbor. Having duplicate entries for the same holiday period may result in duplicate academic years and term dates within Arbor. Arbor works best with reporting if there is only three terms per year
4.3 | Assessment | If using the current MIS for school bespoke assessment, download assessment marks before the final migration (and after the last data drop is done on the current MIS) | Arbor migrates statutory key stage assessments but any bespoke assessments will not migrate. Assessments will need to be created on Arbor (previous marks can then be imported after creation) Click here for more information

## 3. Data Counts
Data Counts
Use this page to help you compare the data in your previous system, to what we have migrated into your new Arbor MIS. You can also use the Data Migration Report you can download from Arbor to help with this. We also have further guidance here.
Field | What should I count? | Number in SIMs | Number in Arbor | Checked By | Status
Enrolment | Count of whole school enrolment | e.g 307 | e.g 307 | e.g Joe Bloggs
Count of enrolment by Year Group
Count of enrolment by Registration Form
Demographic | Count of students with FSM status
Count of students with Ever6FSM status
Count of students with Service Child status
Count of students with Pupil Premium eligibility
Count of students with EYPP eligibility
Count of students with Service Child status
SEN | Count of students with SEN Status
Count of Students by SEN Need To check this in Arbor navigate to Students > Educational Needs > Students with SEN > SEN Needs
Staff | Count of staff this academic year To check this in Arbor navigate to School > All Staff > Single Central Record
Attendance | Percentage Present for Academic YTD To check this in Arbor navigate to Students > Attendance > Statistics > Use filter to change date and type
Percentage Absent for Academic YTD To check this in Arbor navigate to Students > Attendance > Statistics > Use filter to change date and type
Percentage Authorised Absent for Academic YTD To check this in Arbor navigate to Students > Attendance > Statistics > Use filter to change date and type
Percentage Unauthorised Absent for Academic YTD To check this in Arbor navigate to Students > Attendance > Statistics > Use filter to change date and type
Student Profiles | Check a random sample of 5 student profiles - check that everything has migrated as expected including Guardian information. The list should include students from the following groups: FSM, In-Care, Service and are from a range of year groups. Check Welsh-specific fields for students as outlined in the Data cleansing tab. Search for the student's name in the search box or go to Students > All Students > Browse Students to start checking. Click here and here for FAQ's
Staff Profiles | Check a random sample of 10 staff profiles. Check everything on their profile including DOB, Address, Teacher Number, checks/qualifications, NI numbers etc. Check Welsh-specific fields for staff as outlined in the Data cleansing tab. Search for the staff name in the search box or go to School > All Staff > Browse Staff
Staff Business Roles & Permissions | Check that all of your staff members Business Roles and Permissions are correct Click here for more guidance
Leavers | Compile a list of students who have left the school since the backup date Click here for more information
Excluded Students | Compare lists of students with Temporary and Permanent exclusions Students > Behaviour > Fixed Period Exclusions/Permanent Exclusions
Persistent Absentees | Compare lists of PA students and their attendance figures Students > Attendance > Persistent Absentees
In-care Students | Compare lists of students in care and their guardian details Students > Demographics > Looked After (In Care) Clicl here for more information
Staff Absence | Compare staff absence statistics School > All Staff > Absences > Change the dates on the filter Click here for more information
Guardians | Compile a list of Guardians marked as 'do not contact'

## 4. Training Checklist
Training Checklist
Use this page to keep track of the training you need to complete. All the training you have purchased is available to book via The Arbor Training Hub.
Click here to access The Arbor Training Hub
About the training
To help you hit the ground running, your Project Lead already has an account on The Arbor Training Hub. They have access to all the training your school has purchased. This includes the Arbor Foundations Training. This is a series of self-paced, essential e-learning sessions (listed below) that are designed to make sure everyone feels confident with the basics of Arbor. If you need a little extra help, we also run Live Training Clinics twice a day, which are available to book via The Training Hub, to ask our experts any questions about the training you've completed. Your Project Lead can also use the Hub to book any extra training you may have purchased, such as Meals, Payments, or Assessments.
Teacher Training
Teachers don't normally need access to the Arbor Training Hub - You can share these training videos with them instead - Getting Started and Teacher Essentials
Arbor Foundations Training
You must complete the below courses before you Go Live with Arbor - they are in the "Pre-Go Live" learning path on the Training Hub
Course Name | Description |  | Approximate Duration | Status
Getting Started | Aimed at all Arbor MIS users, this course will introduce you to Arbor and explain how to access support, if needed. You will explore the Arbor Navigation menus, how to access and understand your home Dashboard and KPIs, and get top tips from our Customer Education Specialists. |  | 13 mins
Student Profiles and Adding Demographics | Aimed at School Administrators, this course will show users how to navigate and edit Student Profiles, including where additional information, such as SEND and Medical, can be stored and administered. |  | 90 mins
Staff Business Roles and Permissions | Aimed at School Administrators, this course will allow you to manage new and existing users and their Business Roles and Permissions effectively in Arbor. |  | 45 mins
Primary Attendance Management | Aimed at Attendance Officers and School Administrators, this course will deep-dive into Arbor's Attendance Module, getting you ready for day one. |  | 90 mins
Communications | Aimed at Office Managers and School Administrators, this course will teach you how to set up and manage your school Communications in Arbor. |  | 90 mins
You can complete the below courses after you Go Live with Arbor if you wish, they are in the "Post Go-Live" learning path in the Training Hub
Course Name | Description |  | Approximate Duration | Status
Guardian Profiles | Aimed at School Administrators this course will show users how to add and manage Guardian information. We recommend completing the Student Profiles course before starting this course. |  | 45 mins
Staff Profiles | Aimed at School Administrators, this course will allow users to add, find, edit and navigate Staff Profiles. |  | 60 mins
Attendance Reporting | Aimed at Attendance Officers and School Administrators, this course will give you a deep-dive view of Arbors' Attendance Module's reporting tools. |  | 60 mins
Staff Absence and Cover | Aimed at Office Administrators and Cover Managers this course will show users how to record and report on Staff Absence, set Cover, and manage Supply. |  | 60 mins
Arbor MIS Management | Aimed at Office Administrators and Cover Managers this course will show users how to record and report on Staff Absence, set Cover, and manage Supply. |  | 15 mins
Adding Students and CTFs | Aimed at School Administrators, this course will allow users to manage student Enrolment, including CTFs, ready for day one. |  | 60 mins
Single Central Record | Aimed at School Administrators, this course shows users how the Single Central Record can be stored in Arbor. |  | 15 mins
Staff Contracts and Payscales | Aimed at Administrators and HR staff, this session will show users how to add Employment and Financial information including Contracts, Checks, Pay Scales, Positions, Allowances, and Superannuation Schemes. |  | 75 mins
Custom Groups | Aimed at Data Managers and School Administrators, this course will teach you how to create, manage and use Custom Groups in Arbor. |  | 15 mins
User Defined Fields | Aimed at Data Managers and School Administrators, this course will teach you how to create and manage User-Defined Fields in Arbor. |  | 10 mins
School Reporting | Aimed at Senior Leaders, Business and Data Managers, this course will teach you where to find and use the in-built analysis tools, helping you locate key School Statistics. |  | 20 mins
Custom Report Writer | Aimed at all Staff who would like to learn how to use the in-built Custom Report Writer features to build bespoke reports. |  | 75 mins
Arbor AI Overview | This course, aimed at Project Leads and School Administrators, will introduce you to Arbor AI, its features, and how to manage them. |  | 10 mins
Arbor AI Modules | Aimed at all MIS users, this course will introduce you to the Arbor AI features in the available modules. |  | 20 mins
Additional and Bespoke Training
You may have purchased some additional training to help get you up and running with modules such as Meals and Payments in Arbor. You may also have purchased Bespoke Training such as Assessment or Behaviour Training. Any additional training will automatically be added to the Project Lead's Training Hub account. If you would like to discuss purchasing any of the additional training listed below, please contact customersales@arbor-education.com
Additional Training (Meals/Payments/Parent App)
Course Name | Description | Course Type | Duration | Status
Arbor Foundations: Meals Setup and Management | Aimed at School Administrators and Office Managers, this course will teach you how to setup and manage your Meals offering in Arbor. | Live Session | 90 mins
Arbor Foundations: Payments Setup and Management | Aimed at Business Managers and/or Finance Managers, this course will guide you through setting up your system for card payments and managing your accounts and balances. | Live Session | 90 mins
Arbor Foundations: Parental Engagement | Aimed at School Administrators and Office Managers, this course will show you how to set up and use the Parent App and Parent Portal to manage your communication and engagement with Parents and Guardians. | E-Learning & Live Sessions | 3 hours
Arbor Foundations: Payments Plus | Aimed at School Administrators and Office Managers, this course will teach you how to setup and create your rotating meal menus to allow your parents to select their child's meal choices from the parent portal. | Live Session | 45 mins
Bespoke Training (Assessments/Behaviour/Reporting)
Course Name | Description | Course Type | Duration | Status
Behaviour Consultation and Reporting | Aimed at Behaviour Leads, this consultative course will show you how to set up and manage behaviour in Arbor based on your requirements. | Click here for more info | Click here for more info
Assessment Consultation | Aimed at the Assessment Lead/decision maker - you'll discuss how you'd like to manage your assessments in Arbor. | Click here for more info | Click here for more info
Operational Reporting | Aimed at Headteachers and Senior Leaders, this session will teach you how to report on key areas in Arbor. | Click here for more info | Click here for more info
More Information: How to book 1-1 sessions
Training Test Site
You can put what you have learnt in your training sessions to the test, using our Arbor Training Test Site - this is a real Arbor system with test data pre-loaded into the system. It looks and works the same as a real Arbor MIS, so is the perfect way to familiarise yourself with Arbor ahead of your migration and Go Live. The link to access the site, as well as long in details can be found in the Arbor Training Hub, in the 'Getting Started' course.

## 5. Important Checks for Migrati
Important Information for a Success Migration to Arbor using Groupcall Xporter On Demand App
There are key things you need to check or ensure you have setup to ensure that your migration to Arbor using Xporter is successful Use the checklist below to ensure you have completed all of these for a successful migration to Arbor
What should I check? | Why is this important | How to check this | Additional Info | Checked | Owner
Review Server Pre Reqs | To ensure your SIMS server is ready for the migration | Review our Groupcall Migration Pre Requisites to ensure your SIMS server is ready for the Migration |  | FALSE | Schools Project Lead/IT Lead
Approve Arbor T&Cs | If you haven't approved our Terms & Conditions in week 2 of your onboarding journey, we won't be able to start your migration on time. Accepting our T&Cs gives us the green light that you're happy to proceed with the migration. | You'll need to log into your Secure Portal (instructions sent via email) and accept T&Cs. | Click here for more information | FALSE | Schools Project Lead
Approve Data Sharing with Arbor via Groupcall Xporter | Your migration is being facilitated by Groupcall and Arbor so you'll need to approve data sharing with Arbor via Groupcall. Failure to do this will mean we won't be able to see your data and start your migration on time. | Groupcall have sent you an email asking you to approve data sharing with Arbor. Follow the steps outlined in the email to action this. | Click here for more information on Arbor help centre Click here for more information on Groupcall help centre | FALSE | Schools Project Lead
Check Permissions in SIMS | The person who accepts the data sharing agreement needs permissions to access all the relevent data we will migrate in SIMS. | Check that the user who approves the data-sharing agreement has access to the following areas of SIMS: - Assessment Co-ordinator - Cover Manager - School Administrator - Senior Management Team - Personnel Officer* - Third-Party Reporting *Personnel Officer is the recommended permission for maximum compatibility, however, if you are not comfortable with this permission, Personnel Data Exporter can be substituted. Read Groupcalls guidance for further information: Best Practices: Xporter and MIS Permissions. If any of these are missing please make sure they are added to the SIMS user before your migration. | Click here for more information on how to check permissions | FALSE | Schools Project Lead
Install Xporter on Demand | We use Groupcall Xporter on Demand to facilitate the migration, without this installed we cannot start your migration on time Important: If your SIMS server is hosted by your Local Authority or if you require 3rd Party Technical assistance, please contact your IT team directly regarding your required XoD installation and to contact us to assist. | You will receive an email from xodlive@groupcallalert.com with the subject “Invitation from Arbor Education to sync your MIS data and complete your setup”. Follow all steps to install XoD as soon as you receive this email. We recommend using the Guided Install option and scheduling a call with Groupcall to ensure everything is set up correctly. Important: Some schools already use Xporter to connect other 3rd party applications to the MIS. If you already use Xporter on Demand you won’t need to install it again. | Click here for more information - refer to step 5 and onwards How to install Xporter | FALSE | Schools Project Lead/IT Lead
Book Guided Install of Xporter on Demand | There are two options when installing Groupcall Xporter on Demand: Self Install or Guided Install, we recommend booking a guided install so Groupcall can install on your behalf | After you have approved data sharing, you can choose to select a ‘self install’ or book an onboarding slot with the Groupcall support team, who will call you to request remote access to the SIMS server and install XoD on your behalf - this is the recommended approach. | Refer to Step 5 and onwards here | FALSE | Schools Project Lead/IT Lead
Check Server Capacity for Install of Groupcall Xporter on Demand | We highly recommend installing Groupcall Xporter on Demand on a server. Installing on a workstation can result in poor uptime of integrated services. | Click here to view Server Pre Requisists from Groupcall. |  | FALSE | Schools Project Lead/IT Lead
Leave Server Switched On | If the server or workstation that Groupcall is installed onto, is switched off we will not be able to complete the migration as we cannot access the data | Ensure the Server or Workstation that is running Groupcall Xporter on Demand remains on for the duration of the migration, even if this is over a weekend/holiday |  | FALSE | Schools Project Lead/IT Lead
Availability During Holidays | Ensure someone is available via email over the holiday in your school. Ideally the Project Lead or IT Lead should be available to check their e-mail during the holidays to ensure they can pick up any important information about the migration status and success. | Check with your team if someone will be available to check their emails during the holiday to check migration progress/sucess. |  | FALSE | Schools Project Lead/IT Lead