## Data Entry Checklist
Site Setup & Data Entry Checklist
Use this checklist to keep track of your progress when entering data into your blank Arbor MIS - all data listed below will need to be added into your Arbor site by the school Project Lead and you can access the relevant training videos via the Manual Migration course in the Arbor Training Hub.
School Details and Pastoral Structure | When to add | How to add | Training | Progress
School Details | Week 1 | Manually | Week 1 | Complete
Academic Years | Week 1 | Manually | Week 1 | Delayed
Term Dates | Week 1 | Manually | Week 1 | In Progress
Holidays | Week 1 | Manually | Week 1
Year Groups | Week 1 | Manually | Week 1
Registration Forms | Week 1 | Manually | Week 1
Houses | Week 1 | Manually | Week 1
Staff Information | When to add | How to add | Training | Progress
Staff Information | Week 2 | Entity Importer | Week 3
Pay Scale | Complete by week 6 | Entity Importer
Pay Scale Spinal Point | Complete by week 6 | Entity Importer
Staff Contract | Complete by week 6 | Entity Importer
Staff Absence | Complete by week 6 | Entity Importer
Staff Check | Complete by week 6 | Entity Importer
Staff Qualification | Complete by week 6 | Entity Importer
Teacher Status | Complete by week 6 | Manually
Staff Next of Kin | Not required by Census | Manually
Staff Vehicle | Not required by Census | Manuall
Student Data | When to add | How to add | Training | Progress
Add an Intake Season | Week 4 | Manually | Week 4
Import all Student CTF's (previous & current academic year) | Week 4 | CTF Import | Week 4
Enrol students from this Current Academic Year onto your Arbor Site | Week 4 | Manually | Week 4
Off-role students that have left mid-year | Complete by week 6 | Manually | Week 4
Correct start dates for those that started mid-year | Complete by week 6 | Completed by Onboarding Team | Week 4
Dietary Requirements | Complete by week 6 | Entity Importer
Disability Access Funding | Complete by week 6 | Entity Importer
Early Years Pupil Premium Recipient | Complete by week 6 | Entity Importer
Fixed Period Exclusions | Complete by week 6 | Entity Importer
Hours At Setting | Complete by week 6 | Entity Importer
Medical Conditions | Complete by week 6 | Entity Importer
Permanent Exclusion | Complete by week 6 | Entity Importer
Top Up Funding | Complete by week 6 | Entity Importer
Post Looked After Arrangements | Complete by week 6 | Manually
Young Carer | Complete by week 6 | Entity Importer
Guardian Relationship Template | Complete by week 6 | Entity Importer
Student Consents | Complete by week 6 | Manually
Student Linked documents | Complete by week 6 | Manually
Student Pastoral Note Template | Complete by week 6 | Entity Importer
Attendance Data (Roll Call Marks) | By next census | Entity Importer

## Readiness for Go-Live Checklist
Readiness for Go-Live Checklist
This tab will act as a checklist for you and your school, to ensure that you've completed key tasks before going live with your Arbor MIS. Complete and tick-off the tasks to make sure your first day with Arbor is a success!
Site Setup | Complete?
Complete your site setup training videos on the Arbor training hub | FALSE
Add all census required data in the main areas below: - Year Groups and Registration Forms - Term Dates and Holidays - Student Enrolment - Student Data - Guardian Data - Staff Data | FALSE
Ensure all required 3rd party applications/providers are ready to connect | FALSE
Confirm that your registers are available for day 1 by going to Students > Attendance > Registers by Date | FALSE
Staff preparation
Make sure staff members have the correct Business Roles & Permissions - use this article for guidance | FALSE
Ensure all staff have their work email address set as their 'default' email address to make sure they can get logged in | FALSE
Share your URL with all staff, ahead of your go live day along with this helpful guide on how to log in for the first time | FALSE
Ensure Teachers are assigned to their registration forms so that they can take attendance - Assign tutors to registration forms | FALSE
Helpful guides to help you prepare for Go-Live
Teachers Guide
Admin Guide
Readiness for Go Live Checklist