## Set Up Overview
Site Setup & Data Entry Checklist
Use this checklist to keep track of your progress when entering data into your blank Arbor MIS - all data listed below will need to be added into your Arbor site by the school Project Lead and you can access the relevant training videos via the Brand New Site Setup course in the Arbor Training Hub.
School Information | Training video | When to add | Owner at School | Progress
Term Dates | Setting up your Schools details and pastoral structure | Week 1
Holidays | Setting up your Schools details and pastoral structure | Week 1
Year Groups | Setting up your Schools details and pastoral structure | Week 1
Registration Forms | Setting up your Schools details and pastoral structure | Week 1
Houses | Setting up your Schools details and pastoral structure | Week 1
Student Information | Training video | When to add | Owner at School | Progress
Add students by CTF or Applicant Import Spreadsheet | Managing Student Profiles | Week 2
Add Student enrolment information | Managing Student Profiles | Week 2
Funded Hours/ Hours at Setting/ Extended Entitlement Hours Information | Managing Student Profiles | Week 3
Disability Access Fund Indicator | Managing Student Profiles | Week 3
Early Years Pupil Premium Recipient Indicator | Managing Student Profiles | Week 3
Top up Fund Indicator | Managing Student Profiles | Week 3
Post Looked After Arrangements | Managing Student Profiles | Week 3
Medical Conditions | Managing Student Profiles | Week 3
Dietary Requirements | Managing Student Profiles | Week 3
Consents (Not required for census) | Managing Student Profiles | Week 3
Pastoral notes, linked documents (Not required for census) | Managing Student Profiles | Week 3
Guardian Information | Training video | When to add by | Owner at School | Progress
Add Guardian information | Guardian Profiles | Week 4
Add Guardian contact details | Guardian Profiles | Week 4
Staff Information | Training video | When to add by | Owner at School | Progress
Staff Details | Managing Staff Profiles | Week 4
Teacher/ TA status | Managing Staff Profiles | Week 4
Other staff data, including disability etc. | Managing Staff Profiles | Week 4
Qualifications | Staff Contracts and Payscales | Week 4
Payscales | Staff Contracts and Payscales | Week 4

## Setup Overview (Improved) (hidden)
Data
Included in this tab is a list of all the important data that you will need to add to your Arbor site in readiness to take attendance on day 1! As part of your training, (available to access in the Arbor Training Hub - Brand New School Site Setup Training) you will go through short snippet videos that will go through how to add your key data to your Arbor site. Following each video, you should then add your data to your site using this tab to keep track of your progress. Please note: It may be that some of this information is not relevant for you or does not need to be added to your Arbor site, for example, if you are not using Arbor to manage staff HR/Contracts, you won't need to add this into Arbor.
Data to add to your Arbor site:
| School Details and Pastoral Structure | Progress | Owner | Due Date
| Term Dates |  | School
| Holidays |  | School
| Year Groups |  | School
| Registration Forms |  | School
| Houses |  | School
| Student Information | Progress | Owner | Due Date
| Add students by CTF or Applicant Import Spreadsheet |  | School
| Add Student enrolment information |  | School
| Funded Hours/ Hours at Setting/ Extended Entitlement Hours Information |  | School
| Disability Access Fund Indicator |  | School
| Early Years Pupil Premium Recipient Indicator |  | School
| Top up Fund Indicator |  | School
| Post Looked After Arrangements |  | School
| Medical Conditions |  | School
| Dietary Requirements |  | School
| Consents (Not required for census) |  | School
| Pastoral notes, linked documents (Not required for census) |  | School
| Guardian Information | Progress | Owner | Due Date
| Add Guardian information |  | School
| Add Guardian contact details |  | School
| Staff Information | Progress | Owner | Due Date
| Staff Details |  | School
| Teacher/ TA status |  | School
| Other staff data, including disability etc. |  | School
| Qualifications |  | School
| Payscales |  | School

## Third Party System Audit (hidden)
System Audit
We can integrate with Third Party Applications in three ways:
1. Manual sync from Arbor |  | For Applications that do not offer an automated integration, Arbor can help you to keep your application updated by uploading a report. Please see column 'Additional Notes & next steps' for the link to the help centre to show you how to integrate with each application where a manual sync is required. We will update the links for you when your third parties have been listed. NOTE: You will need to contact your Application Provider to let them know of your move to Arbor!
2. Direct Arbor API |  | Some companies choose to integrate directly with Arbor's API, others choose to do this via a company such as Groupcall or Wonde. If the integration listed in the 'solution' column is either 'Arbor API' or 'Third Party API', the method of connecting for the school is the same. Please click here for instructions on how to connect. Note: Either the school or the Trust (depending on who's managing the integrations in your programme) will need to contact the application provider directly and inform them of your move to Arbor. They will advise you further on the next steps from their end.
3. Third Party API
List all of the applications that your schools currently use:
Application Name | Provideer | Replace with Arbor? | When do you plan to replace? | What does the application do? | School(s) | Cost of Application | Appliation Renewal Date | Sync Status | Solution | Owner | Notified Application of Move to Arbor? | Go Live Date for integration | Additional Notes and Next Steps
e.g. CPOMS |  | No Replacement | e.g. School Go Live, December 19 etc. | e.g. Safeguarding |  | e.g. £0.00 | e.g. 01/04/2020 | Pending | Arbor API | e.g. School | ✓ Yes | e.g. 10/10/2017 | e.g. School required day one
[8 empty] | Pending | Manual Integration |  |  |  | Full Help Centre Guide
[8 empty] | Pending | Third party API |  |  |  | Full Help Centre Guide
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending

## Trust Implementation Plan & Tim (hidden)
Trust Timeline Plan
| Aims | Status | Owner | Milestones | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Discover & Plan
| Handover to implementation |  | Arbor Programme Lead | • MAT Kick Off • MAT Discovery • Implementation & Shared Success Plans • Coordinated Training Plans • Plan for third party applications • Fornightly Progress Calls | bar: Week 1
| Complete Kick Off Call |  | Arbor Programme Lead & MAT Team | bar: Week 1
| Complete MAT discovery day & needs requirement, including trusts approach to trust & school alignment |  | Arbor Programme Lead & MAT Team
| Identify roles & responsibilities & plan for risk management |  | Arbor Programme Lead & MAT Team
| Identify phase 1 schools and Arbor Champions |  | MAT Team
| Confirm MAT and school implementation plan and objectives |  | Arbor Programme Lead & MAT Team
| Training needs analysis for teaching and support staff & confirm training plan for schools |  | Arbor Programme Lead & MAT Team
| School/ MAT contacts all third party integrations prior to go live |  | School Team & MAT Team
| Commence Fortnightly Progress Calls |  | Arbor Programme Lead & MAT Team
| Communicate roll out plan & training plans to schools |  | MAT Team
| School Implementation Kicks Off |  | Arbor Programme Team & MAT Team
Deployment
| Schools complete Arbor pre launch implementation |  | School Team | • Data Checks & Counts • Training • Data Migration • School Go Lives • Weekly School Project Progress Calls • Fortnightly MAT Project Progress Calls • Performance Reporting | bar: Week 1
| Schools complete Arbor training |  | School Team | bar: Week 1 to Week 2
| Schools complete data checks & counts |  | School Team | bar: Week 1
| School/ MAT completes final data migration |  | School Team & MAT Team | bar: Week 1
| Arbor releases school sites |  | Arbor Programme Team | bar: Week 4
| School signs off data migration report |  | School Team | bar: Week 4
| Commence schools weekly project progress calls |  | Arbor Programme Team & School Team | bar: Week 4
| Coordination of service packages |  | Arbor Programme Team & MAT Team | bar: Week 4
| Onsite Half Term Performance Reporting |  | Arbor Programme Lead & MAT Team | bar: Week 6 to Week 7
Growth
| Continued delivery of service packages & training |  | Arbor Programme Team & MAT Team | • Final Review • Graduation
| Adoption of best practice with the support of the Arbor community |  | School Team
School Graduation
Final review of programme success, performance & impact reporting
Trust Graduation

## Training Plan (hidden)
MAT Training Plan
Here we will keep a handy list of all of your proposed, booked and completed training sessions:
Please note that online training sessions will have additional breaks if longer than one hour, so three hours of online training will require 3.5 hours of total training time allocated.
Purchased Training | Is the session split? | Who is the training for? | Agenda | Booked date/time | Link to attend training | Status | Notes | Logged on GS? (Arbor Internal)
1 x InPerson Primary PreLaunch training : School Ops | Part 1 | MAT central team | Click here for agenda |  |  |  |  | FALSE
| Part 2 | MAT central team
Online Primary Post Launch Training : School Ops | Part 1 |  | Click here for agenda |  |  |  |  | FALSE
Part 2
In-Person Assessment Consultation (Half Day) | Part 1 |  | Click here for agenda
| Part 2 | [6 empty] | FALSE
In-Person Assessment Setup Training (Half day) | Part 1 |  | Click here for agenda |  |  |  |  | FALSE
Part 2
In-Person Assessment Analysis Training (Half day) | Part 1 |  | Click here for agenda
Part 2
School Payments | 1/2 day |  | Click here for agenda
School Meals | 1/2 day |  | Click here for agenda
Online Group MIS Training |  |  | Click here for agenda

## School Site Setup Agenda (hidden)
Session | Details | Time
New School Site Setup 1: School Details and Pastoral Structure | This session covers the following topics: •Setting up School Details •Creating previous Academic Calendars •Adding Staff Profiles •Setting and checking Business roles & Permissions •Setting up last year's Pastoral Structure (Year Groups and Reg Forms) | 60 mins
New School Site Setup 2: Student Enrolment | This Session covers the following topics: •Creating an Intake Season •Adding students to Intake Season via CTF or manually •Enrolling Applicants (students) •Amending student start dates •Managing School Leavers | 60 mins
Student Profiles and Guardian Profiles | This session covers the following topics: •Navigating Student Profiles •Adding and Amending Data on a Student Profile (inlcuding information required for first school census) •Adding Exclusions •Adding and accessing Guardian Profiles •Bulk updating Guardian Profiles ( Contact details, Authorised to Collect) •Editing Guardian Profiles (including Student/Guardian relationships (Primary/Legal status)) | 1hr 30 mins
Staff Profiles and Absences | This session covers the following topics: •Navigating Staff Profiles •Adding and amending data on a Staff Profile •Logging Staff Absences •Reporting on Staff Absences | 60 mins
Staff HR and Admin | This sessions covers the following topics: •Adding and amending Staff Contracts •Managing Positions •Managing Payscales and Allowances •Ending staff employment | 60 mins

## Data Migration & School Details (hidden)
Data Migration
School Name | Current System | Phase | Link to school's implementation workbook | Last day of term | Go Live Date | Kick off call booked? | Kick off call complete? | Arbor Secure Portal for back ups to be sent | Data Uploaded | Site Released
| SIMS | Special |  |  |  | FALSE | FALSE |  | FALSE | FALSE
| SIMS | Secondary |  |  |  | TRUE | TRUE |  | FALSE | FALSE
| SIMS | Primary |  |  |  | FALSE | FALSE |  | FALSE | FALSE
| SIMS | Special |  |  |  | FALSE | FALSE |  | FALSE | FALSE
| N/A |  |  |  |  | FALSE | FALSE |  | FALSE | FALSE
| N/A |  |  |  |  | FALSE | FALSE |  | FALSE | FALSE
| N/A |  |  |  |  | FALSE | FALSE |  | FALSE | FALSE
| N/A |  |  |  |  | FALSE | FALSE |  | FALSE | FALSE
Click here to view our full help centre article on sending your SIMS back up

## Readiness for go live - Checkli
Readiness for Go-Live Checklist
This tab will act as a checklist for you and your school, to ensure that you've completed key tasks before going live with your Arbor MIS. Complete and tick-off the tasks to make sure your first day with Arbor is a success!
Site Setup | Complete?
Complete your site setup training videos on the Arbor training hub | FALSE
Add all census required data in the main areas below: - Year Groups and Registration Forms - Term Dates and Holidays - Student Enrolment - Student Data - Guardian Data - Staff Data | FALSE
Ensure all required 3rd party applications/providers are ready to connect | FALSE
Confirm that your registers are available for day 1 by going to Students > Attendance > Registers by Date | FALSE
Staff preparation
Make sure staff members have the correct Business Roles & Permissions - use this article for guidance | FALSE
Ensure all staff have their work email address set as their 'default' email address to make sure they can get logged in | FALSE
Share your URL with all staff, ahead of your go live day along with this helpful guide on how to log in for the first time | FALSE
Ensure Teachers are assigned to their registration forms so that they can take attendance - Assign tutors to registration forms | FALSE
Helpful guides to help you prepare for Go-Live
Teachers Guide
Admin Guide
Readiness for Go Live Checklist