## Data Entry Checklist
Site Setup & Data Entry Checklist
Use this checklist to keep track of your progress when entering data into your blank Arbor MIS - all data listed below will need to be added into your Arbor site by the school Project Lead and you can access the relevant training videos via the Manual Migration course in the Arbor Training Hub.
School Details and Pastoral Structure | When to add | How to add | Spaces task containing training | Progress
School Details | Week 1 | Manually | 03 - Complete Week 1 Training and Site Set-up | Complete
Academic Years | Week 1 | Manually | 03 - Complete Week 1 Training and Site Set-up | Delayed
Term Dates | Week 1 | Manually | 03 - Complete Week 1 Training and Site Set-up | In Progress
Holidays | Week 1 | Manually | 03 - Complete Week 1 Training and Site Set-up
Year Groups | Week 1 | Manually | 03 - Complete Week 1 Training and Site Set-up
Registration Forms | Week 1 | Manually | 03 - Complete Week 1 Training and Site Set-up
Houses | Week 1 | Manually | 03 - Complete Week 1 Training and Site Set-up
Staff Information | When to add | How to add | Spaces task containing training | Progress
Staff Information | Week 2 | Entity Importer - Staff Template | 05 - Complete Week 3 Training and Site Set-up
Pay Scale | Complete by week 6 | Entity Importer - Pay Scale Template | 05 - Complete Week 3 Training and Site Set-up
Pay Scale Spinal Point | Complete by week 6 | Entity Importer - Pay Scale Template | 05 - Complete Week 3 Training and Site Set-up
Staff Contract | Complete by week 6 | Entity Importer - Staff Contract | 05 - Complete Week 3 Training and Site Set-up
Staff Absence | Complete by week 6 | Entity Importer - Staff Absence | 05 - Complete Week 3 Training and Site Set-up
Staff Check | Complete by week 6 | Entity Importer - Staff Check | 05 - Complete Week 3 Training and Site Set-up
Staff Qualification | Complete by week 6 | Entity Importer - Staff Qualification | 05 - Complete Week 3 Training and Site Set-up
Teacher Status | Complete by week 6 | Manually
Staff Next of Kin | Not required by Census | Manually
Staff Vehicle | Not required by Census | Manually
Student Data | When to add | How to add | Spaces task containing training | Progress
Add an Intake Season | Week 4 | Manually | 06 - Complete Week 4 Training and Site Set-up
Import all Student CTF's (previous & current academic year) | Week 4 | CTF Import | 06 - Complete Week 4 Training and Site Set-up
Enrol students from this Current Academic Year onto your Arbor Site | Week 4 | Manually | 06 - Complete Week 4 Training and Site Set-up
Off-role students that have left mid-year | Complete by week 6 | Manually | 06 - Complete Week 4 Training and Site Set-up
Correct start dates for those that started mid-year | Complete by week 6 | Completed by Onboarding Team | 06 - Complete Week 4 Training and Site Set-up
Dietary Requirements | Complete by week 6 | Entity Importer | 06 - Complete Week 4 Training and Site Set-up
Disability Access Funding | Complete by week 6 | Entity Importer | 06 - Complete Week 4 Training and Site Set-up
Early Years Pupil Premium Recipient | Complete by week 6 | Entity Importer | 06 - Complete Week 4 Training and Site Set-up
Fixed Period Exclusions | Complete by week 6 | Entity Importer | 06 - Complete Week 4 Training and Site Set-up
Hours At Setting | Complete by week 6 | Entity Importer | 06 - Complete Week 4 Training and Site Set-up
Medical Conditions | Complete by week 6 | Entity Importer | 06 - Complete Week 4 Training and Site Set-up
Permanent Exclusion | Complete by week 6 | Entity Importer | 06 - Complete Week 4 Training and Site Set-up
Top Up Funding | Complete by week 6 | Entity Importer | 06 - Complete Week 4 Training and Site Set-up
Young Carer | Complete by week 6 | Entity Importer | 06 - Complete Week 4 Training and Site Set-up
Guardian Relationship Template | Complete by week 6 | Entity Importer | 06 - Complete Week 4 Training and Site Set-up
Student Pastoral Note Template | Complete by week 6 | Entity Importer | 06 - Complete Week 4 Training and Site Set-up
Student Consents | Complete by week 6 | Manually | 06 - Complete Week 4 Training and Site Set-up
Student Linked documents | Complete by week 6 | Manually | 06 - Complete Week 4 Training and Site Set-up
Post Looked After Arrangements | Complete by week 6 | Manually | 06 - Complete Week 4 Training and Site Set-up
Attendance Data (Roll Call Marks) | By next census | Entity Importer | 07 - Complete Week 5 Training and Site Set-up

## Readiness for Go-Live Checklist
Readiness for Go-Live Checklist
This tab will act as a checklist for you and your school, to ensure that you've completed key tasks before going live with your Arbor MIS. Complete and tick-off the tasks to make sure your first day with Arbor is a success!
Site Setup | Complete?
Complete your site setup training videos on the Arbor training hub | FALSE
Add all census required data in the main areas below: - Year Groups and Registration Forms - Term Dates and Holidays - Student Enrolment - Student Data - Guardian Data - Staff Data | FALSE
Ensure all required 3rd party applications/providers are ready to connect | FALSE
Confirm that your registers are available for day 1 by going to Students > Attendance > Registers by Date | FALSE
Staff preparation
Make sure staff members have the correct Business Roles & Permissions - use this article for guidance | FALSE
Ensure all staff have their work email address set as their 'default' email address to make sure they can get logged in | FALSE
Share your URL with all staff, ahead of your go live day along with this helpful guide on how to log in for the first time | FALSE
Ensure Teachers are assigned to their registration forms so that they can take attendance - Assign tutors to registration forms | FALSE
Helpful guides to help you prepare for Go-Live
Teachers Guide
Admin Guide
Readiness for Go Live Checklist